## COST
COST DATA — Performance by Job
📋 HOW TO USE: Every week, open this sheet and fill in the YELLOW cells by copying numbers from the 'Performance by Job' PDF. Then save the file — the dashboard updates automatically.
REPORT INFO
As of Date (e.g. 17-Jun-26) | 2026-06-17
SVO Number | 201019973010
Week | Week 5
MANHOURS (MHRS)
Plan MHRS | 380
Act Normal Time | 38
Act Over Time | 0
Total Act MHRS | 38
ETC Mhrs | 2567
EAC MHRS | 2605
Variance MHRS | -2225
COST (THB)
Detail | Plan (BG) | Act Cost to Date (A) | Commit (B) | ETC Cost (C) | EAC Cost (A+B+C) | %
Revenue | 1050000 | 437500 |  | 612500 | 1050000
MH Cost | 129040 | 11139 |  | 105742 | 116881 | 11%
Variable Cost | 525000 | 526050 |  |  | 526050 | 50%
└ Material Cost | 525000 | 526050 |  |  | 526050
Total Direct Cost | 654040 | 537189 |  | 105742 | 642931 | 61%
Contribution Margin | 395960 | -99689 |  |  | 407069 | 39%
Allocation Cost |  | 191360 |  |  | 375316 | 36%
Total Cost (Direct + OH) |  | 728548 |  |  | 1018246 | 97%
Gross Margin |  | -291048 |  |  | 31754 | 3%
Total Cost (Inc. SG&A and DP) | 1039924 | 821755 |  |  | 1154446 | 110%
Net Income | 8061 |  |  |  | -104446 | -10%
✏️ Fill in YELLOW cells only. Do NOT add/remove rows or rename this sheet.

## CHART
Week 5
Update : | 2026-06-17 |  | GROUP WEEKLY STATUS |  |  |  |  | Update : | 2026-06-17 |  | LOCATION WEEKLY STATUS
OVERALL PROGRESS |  |  | Master Plan Baseline Rev.0 |  | OVERALL Actual Progress |  |  | No | Region | Group | Tag | RC | Location | Engineering |  |  |  | Construction |  |  |  | Progress
No. | WTG. | Group | Start | Finish | % Plan | % Actual | % Performance | [6 empty] | Boring Log | Survay and Verify | Engineering Doccument | Area Permit | Excavation | Inspection | Re-instate | Package | % Plan | % actual
2 | 30% | B | 2026-05-18 | 2026-07-12 | 4.263% | 2.553% | -1.71%
3 | 20% | C | 2026-06-01 | 2026-07-31 | 1.138% | 1.807% | 0.6695% | [6 empty] | WTG. 15% | WTG. 25% | WTG. 50% | WTG. 10% | WTG. 50% | WTG. 30% | WTG. 10% | WTG. 10% | 100% | 100%
4 | 20% | D | 2026-06-08 | 2026-08-23 | 0% | 1.512% | 1.512% | 1 | 3 | B | B1 | RC04032 | Rojana Industrial Park (Rayong) | 0% | 50% | 10% | 60% | 0% | 0% | 0% | 8% | 15.5% | 7.61%
5 | 20% | E | 2026-05-18 | 2026-06-29 | 0% | 3.372% | 3.372% | 2 |  |  | B2 | RC040321 | Rojana Industrial Park (Rayong) | 0% | 50% | 10% | 60% | 0% | 0% | 0% | 8% | 13.56% | 7.61%
6 | 10% | F | 2026-05-18 | 2026-09-15 | 0% | 0.6176% | 0.6176% | 3 |  |  | B3 | RC0401100001 | Indorama Petrochemical Co., Ltd. | 60% | 50% | 10% | 60% | 0% | 0% | 0% | 8% | 13.56% | 10.31%
Total |  |  |  |  | 5.4% | 9.862% | 4.462% | 4 |  | C | C1 | RC040221 | Amata City Reducing Station | 0% | 50% | 10% | 50% | 0% | 0% | 0% | 8% | 5.688% | 7.31%
ENGINEERING PROGRESS |  |  | Master Plan Baseline Rev.0 |  | ENGINEERING Actual Progress |  |  | 5 |  |  | C2 | RC04011 | Bangkok Polyester Public Co., Ltd. | 60% | 50% | 10% | 75% | 0% | 0% | 0% | 8% | 5.688% | 10.76%
No. | WTG. | Group | Start | Finish | % Plan | % Actual | % Performance | 6 | 1 | D | D1 | RC044041 | Esso (Thailand) Public Co., Ltd. | 0% | 50% | 10% | 66.67% | 0% | 0% | 0% | 8% | 0% | 7.81%
2 | 9% | B | 2026-05-18 | 2026-07-12 | 4.263% | 2.385% | -1.878% | 7 |  |  | D2 | RC044043 | Laem Chabang Industrial Estate | 0% | 50% | 10% | 50% | 0% | 0% | 0% | 8% | 0% | 7.31%
3 | 6% | C | 2026-06-01 | 2026-07-31 | 1.138% | 1.695% | 0.5575% | 8 |  | E | E1 | RC0631100003 | Loyal Haieleung Copper (Thailand) Co., Ltd. | 60% | 100% | 39% | 75% | 0% | 0% | 0% | 8% | 0% | 18.86%
4 | 6% | D | 2026-06-08 | 2026-08-23 | 0% | 1.4% | 1.4% | 9 | 5 |  | E2 | RC410101 | Gangwal Textile Co., Ltd. | 60% | 50% | 39% | 66.67% | 0% | 0% | 0% | 8% | 0% | 14.86%
5 | 6% | E | 2026-05-18 | 2026-06-29 | 0% | 3.26% | 3.26% | 10 | 2 | F | F1 | RC06611 | The Union Mosaic Industry Co., Ltd. | 0% | 46.88% | 10% | 20% | 0% | 0% | 0% | 8% | 0% | 6.176%
6 | 3% | F | 2026-05-18 | 2026-09-15 | 0% | 0.5616% | 0.5616% | Accumulate Plan % | [13 empty] | 5.4%
Total |  |  |  |  | 5.4% | 9.302% | 3.902% | Accumulate Actual % | [14 empty] | 9.862%
CONSTRUCTION PROGRESS |  |  | Master Plan Baseline Rev.0 |  | CONSTRUCTION Actual Progress
No. | WTG. | Group | Start | Finish | % Plan | % Actual | % Performance
2 | 21% | B | 2026-05-18 | 2026-07-12 | 0% | 0.168% | 0.168%
3 | 14% | C | 2026-06-01 | 2026-07-31 | 0% | 0.112% | 0.112%
4 | 14% | D | 2026-06-08 | 2026-08-23 | 0% | 0.112% | 0.112%
5 | 14% | E | 2026-05-18 | 2026-06-29 | 0% | 0.112% | 0.112%
6 | 7% | F | 2026-05-18 | 2026-09-15 | 0% | 0.056% | 0.056%
Total |  |  |  |  | 0% | 0.56% | 0.56%

## DATA
PAI CHART |  |  |  | S-CURVE
% Actual Progress | % Remain |  |  |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Week 79 | Week 80
9.862% | 90.14% |  |  | TOR | Week 0: 0.1%; Week 1: 0.45%; Week 2: 1.5%; Week 3: 2.55%; Week 4: 4.2%; Week 5: 5.95%; Week 6: 8.335%; Week 7: 12.65%; Week 8: 18.29%; Week 9: 24.19%; Week 10: 33.53%; Week 11: 40.9%; Week 12: 47.8%; Week 13: 53.32%; Week 14: 55.45%; Week 15: 57.77%; Week 16: 62.28%; Week 17: 67.86%; Week 18: 73.45%; Week 19: 75.68%; Week 20: 79.86%; Week 21: 83.98%; Week 22: 89.37%; Week 23: 92.74%; Week 24: 95.83%; Week 25: 99%; Week 26: 99.41%; Week 27: 99.82%; Week 28: 100%; Week 29: 100%; Week 30: 100%; Week 31: 100%; Week 32: 100%; Week 33: 100%; Week 34: 100%; Week 35: 100%
|  |  |  | MASTER PLAN | Week 0: 0.1%; Week 1: 1.576%; Week 2: 5.575%; Week 3: 11.66%; Week 4: 20.97%; Week 5: 30.76%; Week 6: 42.07%; Week 7: 52.44%; Week 8: 64.41%; Week 9: 70.09%; Week 10: 75.48%; Week 11: 79.74%; Week 12: 83.75%; Week 13: 88.86%; Week 14: 93.52%; Week 15: 97.74%; Week 16: 99.66%; Week 17: 99.84%; Week 18: 100%; Week 19: 100%; Week 20: 100%; Week 21: 100%; Week 22: 100%; Week 23: 100%; Week 24: 100%; Week 25: 100%; Week 26: 100%; Week 27: 100%; Week 28: 100%; Week 29: 100%; Week 30: 100%; Week 31: 100%; Week 32: 100%; Week 33: 100%; Week 34: 100%; Week 35: 100%
BAR CHART |  |  |  | ACTUAL | Week 0: 0.1%; Week 1: 0.5584%; Week 2: 1.317%; Week 3: 2.5%; Week 4: 5.308%; Week 5: 9.862%
Group | % Plan | % Actual | % Performance
B | 4.263% | 2.553% | -1.71%
C | 1.138% | 1.807% | 0.6695%
D | 0% | 1.512% | 1.512%
E | 0% | 3.372% | 3.372%
F | 0% | 0.6176% | 0.6176%

## LIST
Week | Cut-off Date
Week 0 | 2026-05-13
Week 1 | 2026-05-20
Week 2 | 2026-05-27
Week 3 | 2026-06-03
Week 4 | 2026-06-10
Week 5 | 2026-06-17
Week 6 | 2026-06-24
Week 7 | 2026-07-01
Week 8 | 2026-07-08
Week 9 | 2026-07-15
Week 10 | 2026-07-22
Week 11 | 2026-07-29
Week 12 | 2026-08-05
Week 13 | 2026-08-12
Week 14 | 2026-08-19
Week 15 | 2026-08-26
Week 16 | 2026-09-02
Week 17 | 2026-09-09
Week 18 | 2026-09-16
Week 19 | 2026-09-23
Week 20 | 2026-09-30
Week 21 | 2026-10-07
Week 22 | 2026-10-14
Week 23 | 2026-10-21
Week 24 | 2026-10-28
Week 25 | 2026-11-04
Week 26 | 2026-11-11
Week 27 | 2026-11-18
Week 28 | 2026-11-25
Week 29 | 2026-12-02
Week 30 | 2026-12-09
Week 31 | 2026-12-16
Week 32 | 2026-12-23
Week 33 | 2026-12-30
Week 34 | 2027-01-06
Week 35 | 2027-01-13
Week 36 | 2027-01-20
Week 37 | 2027-01-27
Week 38 | 2027-02-03
Week 39 | 2027-02-10
Week 40 | 2027-02-17
Week 41 | 2027-02-24
Week 42 | 2027-03-03
Week 43 | 2027-03-10
Week 44 | 2027-03-17
Week 45 | 2027-03-24
Week 46 | 2027-03-31
Week 47 | 2027-04-07
Week 48 | 2027-04-14
Week 49 | 2027-04-21
Week 50 | 2027-04-28
Week 51 | 2027-05-05
Week 52 | 2027-05-12
Week 53 | 2027-05-19
Week 54 | 2027-05-26
Week 55 | 2027-06-02
Week 56 | 2027-06-09
Week 57 | 2027-06-16
Week 58 | 2027-06-23
Week 59 | 2027-06-30
Week 60 | 2027-07-07
Week 61 | 2027-07-14
Week 62 | 2027-07-21
Week 63 | 2027-07-28
Week 64 | 2027-08-04
Week 65 | 2027-08-11
Week 66 | 2027-08-18
Week 67 | 2027-08-25
Week 68 | 2027-09-01
Week 69 | 2027-09-08
Week 70 | 2027-09-15
Week 71 | 2027-09-22
Week 72 | 2027-09-29
Week 73 | 2027-10-06
Week 74 | 2027-10-13
Week 75 | 2027-10-20
Week 76 | 2027-10-27
Week 77 | 2027-11-03
Week 78 | 2027-11-10
Week 79 | 2027-11-17
Week 80 | 2027-11-24

## INPUT
|  | WEEK : | Week 5 | [5 empty] | WTG | [5 empty] | TOR PROGRESS | [7 empty] | MASTER PLAN PROGRESS | [7 empty] | ACTUAL PROGRESS | [103 empty] | 2026-05-14 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-09 | 2026-07-16 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-13 | 2026-08-20 | 2026-08-27 | 2026-09-03 | 2026-09-10 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-10 | 2026-12-17 | 2026-12-24 | 2026-12-31 | 2027-01-07 | 2027-01-14 | 2027-01-21 | 2027-01-28 | 2027-02-04 | 2027-02-11 | 2027-02-18 | 2027-02-25 | 2027-03-04 | 2027-03-11 | 2027-03-18 | 2027-03-25 | 2027-04-01 | 2027-04-08 | 2027-04-15 | 2027-04-22 | 2027-04-29 | 2027-05-06 | 2027-05-13 | 2027-05-20 | 2027-05-27 | 2027-06-03 | 2027-06-10 | 2027-06-17 | 2027-06-24 | 2027-07-01 | 2027-07-08 | 2027-07-15 | 2027-07-22 | 2027-07-29 | 2027-08-05 | 2027-08-12 | 2027-08-19 | 2027-08-26 | 2027-09-02 | 2027-09-09 | 2027-09-16 | 2027-09-23 | 2027-09-30 | 2027-10-07 | 2027-10-14 | 2027-10-21 | 2027-10-28 | 2027-11-04 | 2027-11-11 | 2027-11-18 | [7 empty] | 2026-05-14 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-09 | 2026-07-16 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-13 | 2026-08-20 | 2026-08-27 | 2026-09-03 | 2026-09-10 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-10 | 2026-12-17 | 2026-12-24 | 2026-12-31 | 2027-01-07 | 2027-01-14 | 2027-01-21 | 2027-01-28 | 2027-02-04 | 2027-02-11 | 2027-02-18 | 2027-02-25 | 2027-03-04 | 2027-03-11 | 2027-03-18 | 2027-03-25 | 2027-04-01 | 2027-04-08 | 2027-04-15 | 2027-04-22 | 2027-04-29 | 2027-05-06 | 2027-05-13 | 2027-05-20 | 2027-05-27 | 2027-06-03 | 2027-06-10 | 2027-06-17 | 2027-06-24 | 2027-07-01 | 2027-07-08 | 2027-07-15 | 2027-07-22 | 2027-07-29 | 2027-08-05 | 2027-08-12 | 2027-08-19 | 2027-08-26 | 2027-09-02 | 2027-09-09 | 2027-09-16 | 2027-09-23 | 2027-09-30 | 2027-10-07 | 2027-10-14 | 2027-10-21 | 2027-10-28 | 2027-11-04 | 2027-11-11 | 2027-11-18 | time axis 2026-05-14 to 2027-11-18
|  | CUT-OFF DATE : | 2026-06-17 | [35 empty] | 2026-06-17 |  |  |  |  | 1 | 2026-06-10 | 2026-06-17 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10 | 2026-06-17 | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31 | 2027-04-07 | 2027-04-14 | 2027-04-21 | 2027-04-28 | 2027-05-05 | 2027-05-12 | 2027-05-19 | 2027-05-26 | 2027-06-02 | 2027-06-09 | 2027-06-16 | 2027-06-23 | 2027-06-30 | 2027-07-07 | 2027-07-14 | 2027-07-21 | 2027-07-28 | 2027-08-04 | 2027-08-11 | 2027-08-18 | 2027-08-25 | 2027-09-01 | 2027-09-08 | 2027-09-15 | 2027-09-22 | 2027-09-29 | 2027-10-06 | 2027-10-13 | 2027-10-20 | 2027-10-27 | 2027-11-03 | 2027-11-10 | 2027-11-17 | 2027-11-24 | 2026-06-17 |  |  |  |  | 1 | 2026-06-10 | 2026-06-17 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10 | 2026-06-17 | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31 | 2027-04-07 | 2027-04-14 | 2027-04-21 | 2027-04-28 | 2027-05-05 | 2027-05-12 | 2027-05-19 | 2027-05-26 | 2027-06-02 | 2027-06-09 | 2027-06-16 | 2027-06-23 | 2027-06-30 | 2027-07-07 | 2027-07-14 | 2027-07-21 | 2027-07-28 | 2027-08-04 | 2027-08-11 | 2027-08-18 | 2027-08-25 | 2027-09-01 | 2027-09-08 | 2027-09-15 | 2027-09-22 | 2027-09-29 | 2027-10-06 | 2027-10-13 | 2027-10-20 | 2027-10-27 | 2027-11-03 | 2027-11-10 | 2027-11-17 | 2027-11-24 |  |  |  |  | 1 | 2026-06-10 | 2026-06-17 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10 | 2026-06-17 | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31 | 2027-04-07 | 2027-04-14 | 2027-04-21 | 2027-04-28 | 2027-05-05 | 2027-05-12 | 2027-05-19 | 2027-05-26 | 2027-06-02 | 2027-06-09 | 2027-06-16 | 2027-06-23 | 2027-06-30 | 2027-07-07 | 2027-07-14 | 2027-07-21 | 2027-07-28 | 2027-08-04 | 2027-08-11 | 2027-08-18 | 2027-08-25 | 2027-09-01 | 2027-09-08 | 2027-09-15 | 2027-09-22 | 2027-09-29 | 2027-10-06 | 2027-10-13 | 2027-10-20 | 2027-10-27 | 2027-11-03 | 2027-11-10 | 2027-11-17 | 2027-11-24
Group | Location | Activity |  |  |  |  | Work Volumn | [31 empty] | TOR Baseline |  |  |  |  | 2 | Progress |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Week 79 | Week 80 | Master Plan Baseline |  |  |  |  | 2 | Progress |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Week 79 | Week 80 |  | Actual |  |  | 2 | Progress |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Week 79 | Week 80
|  | Phase | Sub Activity |  |  | Remark | QTY. | UNIT | L1 | L2 | L3 | L4 | L5 | L6 | L5 | L6 | L1 | L2 | L3 | L4 | L5 | L6 | L5 | L6 | L1 | L2 | L3 | L4 | L5 | L6 | L5 | L6 | L1 | L2 | L3 | L4 | L5 | L6 | DELAY STATUS |  | Start | Finish | Dru. | 3 | Last Week | This Week | [80 empty] | DELAY STATUS |  | Start | Finish | Dru. | 3 | Last Week | This Week | [81 empty] | Start | Finish | Dru. | 3 | Last Week | This Week | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
[9 empty] | 100% | [7 empty] | 5.4% |  |  |  | 5.4% | 0% |  |  | 30.76% |  |  |  | 21.54% | 9.215% |  |  | 9.862% |  |  |  | 9.302% | 0.56% | 4.462% |  |  |  |  | 4 |  |  | 0.45% | 1.5% | 2.55% | 4.2% | 5.95% | 8.335% | 12.65% | 18.29% | 24.19% | 33.53% | 40.9% | 47.8% | 53.32% | 55.45% | 57.77% | 62.28% | 67.86% | 73.45% | 75.68% | 79.86% | 83.98% | 89.37% | 92.74% | 95.83% | 99% | 99.41% | 99.82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | -20.9% |  |  |  |  | 4 |  |  | 1.576% | 5.575% | 11.66% | 20.97% | 30.76% | 42.07% | 52.44% | 64.41% | 70.09% | 75.48% | 79.74% | 83.75% | 88.86% | 93.52% | 97.74% | 99.66% | 99.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | 4 |  |  | 0.5584% | 1.317% | 2.5% | 5.308% | 9.862% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37% | 11.37%
B | [8 empty] | 30% | 100% | [6 empty] | 4.263% | 14.21% |  |  | 4.263% | 0% |  |  | 7.886% | 26.29% |  |  | 7.886% | 0% |  |  | 2.553% | 8.51% |  |  | 2.385% | 0.168% | -1.71% |  | 2026-05-18 | 2026-07-31 | 75 | 5 |  |  | 0.45% | 1.5% | 2.55% | 3.6% | 4.65% | 6.013% | 9.256% | 13.82% | 18.57% | 25.72% | 29.64% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | -5.333% |  | 2026-05-18 | 2026-07-12 | 56 | 5 |  |  | 0.5143% | 2.036% | 3.986% | 5.936% | 7.886% | 11.79% | 18.3% | 28.27% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% |  | 2026-05-21 | 2026-06-22 | 33 | 5 |  |  | 0% | 0.18% | 0.3164% | 1.097% | 2.553% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213% | 3.213%
3 | B1/3 | RC04032 | Rojana Industrial Park (Rayong) | [6 empty] | 33.33% | 100% | [6 empty] | 5.167% | 15.5% | [6 empty] | 8.857% | 26.57% | [6 empty] | 2.537% | 7.61% |  |  |  | -2.63% | 0.33333 |  |  |  | 6 |  |  | 0.5% | 1.167% | 1.167% | 1.167% | 1.167% | 2.211% | 8.475% | 12.89% | 3.4% | 1.193% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6.32% |  |  |  |  | 6 |  |  | 0.8571% | 2% | 2% | 2% | 2% | 3.91% | 6.456% | 11.52% | 2.596% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 6 |  |  | 0% | 0.2% | 0.2273% | 1.132% | 0.9773% | 1.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 15.5% | 51.67% | [6 empty] | 26.57% | 88.57% | [6 empty] | 7.05% | 23.5% |  |  | -8.45% | 1 | 2026-05-18 | 2026-07-16 | 60 | 7 |  |  | 5% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 1.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -19.52% | 1 | 2026-05-18 | 2026-06-21 | 35 | 7 |  |  | 8.571% | 20% | 20% | 20% | 20% | 11.43% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.345 | 2026-05-21 | 2026-06-22 | 33 | 7 |  |  | 0% | 2% | 2.273% | 10.79% | 8.439% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 7.75% | 51.67% | [6 empty] | 13.29% | 88.57% | [6 empty] | 0% | 0% |  | -7.75% | 0 |  |  |  | 8 | 0.4 | 0.11667 | [80 empty] | -13.29% | 0 |  |  |  | 8 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 51.67% | [5 empty] | 31% |  | 88.57% | [5 empty] | 53.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 9 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 9 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-22 | 2026-06-22 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 51.67% | [5 empty] | 20.67% |  | 88.57% | [5 empty] | 35.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 10 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 10 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 12.92% | 51.67% | [6 empty] | 22.14% | 88.57% | [6 empty] | 12.5% | 50% |  | -0.4167% | 0 |  |  |  | 11 | 0.4 | 0.11667 | [80 empty] | -9.643% | 0 |  |  |  | 11 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 88.57% | [5 empty] | 44.29% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 12 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 12 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-02 | 2026-06-12 | 11 | 12 | 0.81818 | 0.18182 | 0 | 0 | 0.18182 | 0.63636 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 88.57% | [5 empty] | 44.29% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 13 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 13 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 25.83% | 51.67% | [6 empty] | 44.29% | 88.57% | [6 empty] | 5% | 10% |  | -20.83% | 0 |  |  |  | 14 | 0.4 | 0.11667 | [80 empty] | -39.29% | 0 |  |  |  | 14 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 88.57% | [5 empty] | 22.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 15 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 15 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 88.57% | [5 empty] | 22.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 16 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 16 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 17 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 17 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 18 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 18 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 19 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 19 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 19 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 20 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 20 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 5.167% | 51.67% | [6 empty] | 8.857% | 88.57% | [6 empty] | 6% | 60% |  | 0.8333% | 0 |  |  |  | 21 | 0.4 | 0.11667 | [80 empty] | -2.857% | 0 |  |  |  | 21 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 21 | 0.33333 | 0.16667
|  |  |  | AreaOwner 1 KOM PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 22 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 22 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-21 | 2026-05-21 | 1 | 22 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 23 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 23 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 23 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM Rojana |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 24 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 24 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-12 | 2026-06-12 | 1 | 24 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 Submit doc Rojana |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 25 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 25 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-22 | 2026-06-22 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 |  |  | 1 | [5 empty] | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 26 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 26 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 51.67% | [5 empty] | 0% |  | 88.57% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 27 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 27 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-06-24 | 2026-07-19 | 26 | 28 |  | 0 | 0% | 0% | 0% | 0% | 0% | 4.474% | 31.32% | 50.24% | 9.571% | 4.397% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-06-22 | 2026-07-12 | 21 | 28 |  |  | 0% | 0% | 0% | 0% | 0% | 11.86% | 27.67% | 49.35% | 11.12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 28 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 29 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 29 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-24 | 2026-07-05 | 12 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.58333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-05 | 14 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-24 | 2026-07-05 | 12 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.58333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-05 | 14 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 32 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 32 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 36 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-08 | 2026-07-11 | 4 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-19 | 8 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 39 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 39 | 0 | 0 | [80 empty] | 0 |  |  |  | 39 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 40 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 42 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-24 | 2026-07-19 | 26 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038462 | 0.26923 | 0.26923 | 0.26923 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-08 | 2026-07-19 | 12 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.58333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 48 | [87 empty] | 48 | [86 empty] | 48
3 | B2/3 | RC040321 | Rojana Industrial Park (Rayong) | [6 empty] | 33.33% | 100% | [6 empty] | 4.521% | 13.56% | [6 empty] | 8.857% | 26.57% | [6 empty] | 2.537% | 7.61% |  |  |  | -1.984% |  |  |  |  | 49 |  |  | 0.5% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 6.207% | 11.32% | 6.837% | 0.3033% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6.32% |  |  |  |  | 49 |  |  | 0.8571% | 2% | 2% | 2% | 2% | 3.91% | 6.456% | 11.52% | 2.596% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 49 |  |  | 0% | 0.2% | 0.2273% | 1.132% | 0.9773% | 1.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 13.56% | 45.21% | [6 empty] | 26.57% | 88.57% | [6 empty] | 7.05% | 23.5% |  |  | -6.513% | 1 | 2026-05-18 | 2026-07-16 | 60 | 50 |  |  | 5% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 1.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -19.52% | 1 | 2026-05-18 | 2026-06-21 | 35 | 50 |  |  | 8.571% | 20% | 20% | 20% | 20% | 11.43% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.345 | 2026-05-21 | 2026-06-22 | 33 | 50 |  |  | 0% | 2% | 2.273% | 10.79% | 8.439% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 7.75% | 51.67% | [6 empty] | 13.29% | 88.57% | [6 empty] | 0% | 0% |  | -7.75% | 0 |  |  |  | 51 | 0.4 | 0.11667 | [80 empty] | -13.29% | 0 |  |  |  | 51 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 51 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 51.67% | [5 empty] | 31% |  | 88.57% | [5 empty] | 53.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 52 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 52 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-22 | 2026-06-22 | 1 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 51.67% | [5 empty] | 20.67% |  | 88.57% | [5 empty] | 35.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 53 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 53 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 6.458% | 25.83% | [6 empty] | 22.14% | 88.57% | [6 empty] | 12.5% | 50% |  | 6.042% | 0 |  |  |  | 54 | 0.4 | 0.11667 | [80 empty] | -9.643% | 0 |  |  |  | 54 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 88.57% | [5 empty] | 44.29% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 55 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 55 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-02 | 2026-06-12 | 11 | 55 | 0.81818 | 0.18182 | 0 | 0 | 0.18182 | 0.63636 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 88.57% | [5 empty] | 44.29% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 56 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 56 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 25.83% | 51.67% | [6 empty] | 44.29% | 88.57% | [6 empty] | 5% | 10% |  | -20.83% | 0 |  |  |  | 57 | 0.4 | 0.11667 | [80 empty] | -39.29% | 0 |  |  |  | 57 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 88.57% | [5 empty] | 22.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 58 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 58 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 88.57% | [5 empty] | 22.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 59 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 59 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 60 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 60 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 61 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 61 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 62 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 62 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 62 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 88.57% | [5 empty] | 8.857% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 63 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 63 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 5.167% | 51.67% | [6 empty] | 8.857% | 88.57% | [6 empty] | 6% | 60% |  | 0.8333% | 0 |  |  |  | 64 | 0.4 | 0.11667 | [80 empty] | -2.857% | 0 |  |  |  | 64 | 0.68571 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 64 | 0.33333 | 0.16667
|  |  |  | AreaOwner 1 KOM PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 65 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 65 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-21 | 2026-05-21 | 1 | 65 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 66 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 66 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 66 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM Rojana |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 67 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 67 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-12 | 2026-06-12 | 1 | 67 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 Submit doc Rojana |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 68 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 68 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-22 | 2026-06-22 | 1 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 |  |  | 1 | [5 empty] | 20% |  | 51.67% | [5 empty] | 10.33% |  | 88.57% | [5 empty] | 17.71% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 69 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 69 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 51.67% | [5 empty] | 0% |  | 88.57% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 70 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-21 | 35 | 70 | 0.68571 | 0.2 | 0.085714 | 0.2 | 0.2 | 0.2 | 0.2 | 0.11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-07-12 | 2026-07-31 | 20 | 71 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.6% | 47.8% | 29.3% | 1.3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-06-22 | 2026-07-12 | 21 | 71 |  |  | 0% | 0% | 0% | 0% | 0% | 11.86% | 27.67% | 49.35% | 11.12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 71 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 72 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-21 | 10 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-05 | 14 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-21 | 10 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-05 | 14 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 75 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-06 | 2026-07-07 | 2 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 79 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 79 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-27 | 4 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-27 | 4 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 82 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 82 | 0 | 0 | [80 empty] | 0 |  |  |  | 82 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 83 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 83 |  |  | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 83 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 85 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-31 | 8 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-08 | 2026-07-12 | 5 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 91 | [87 empty] | 91 | [86 empty] | 91
3 | B3/3 | RC0401100001 | Indorama Petrochemical Co., Ltd. | [6 empty] | 33.33% | 100% | [6 empty] | 4.521% | 13.56% | [6 empty] | 8.571% | 25.71% | [6 empty] | 3.437% | 10.31% |  |  |  | -1.084% |  |  |  |  | 92 |  |  | 0.5% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 1.167% | 6.207% | 11.32% | 6.253% | 0.8867% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -5.135% |  |  |  |  | 92 |  |  | 0% | 1.071% | 2.5% | 2.5% | 2.5% | 5.195% | 8.789% | 10.21% | 0.563% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 92 |  |  | 0% | 0.2% | 0% | 0.3367% | 2.9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 13.56% | 45.21% | [6 empty] | 25.71% | 85.71% | [6 empty] | 9.75% | 32.5% |  |  | -3.813% | 1 | 2026-05-18 | 2026-07-16 | 60 | 93 |  |  | 5% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 1.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -15.96% | 1 | 2026-05-25 | 2026-06-21 | 28 | 93 |  |  | 0% | 10.71% | 25% | 25% | 25% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.325 | 2026-05-21 | 2026-06-15 | 26 | 93 |  |  | 0% | 2% | 0% | 2.833% | 27.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 7.75% | 51.67% | [6 empty] | 12.86% | 85.71% | [6 empty] | 9% | 60% |  | 1.25% | 0 |  |  |  | 94 | 0.4 | 0.11667 | [80 empty] | -3.857% | 0 |  |  |  | 94 | 0.60714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 94 | 0 | 0.5
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 51.67% | [5 empty] | 31% |  | 85.71% | [5 empty] | 51.43% |  | 100% | [5 empty] | 60% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 95 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 95 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-15 | 2026-06-15 | 1 | 95 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 51.67% | [5 empty] | 20.67% |  | 85.71% | [5 empty] | 34.29% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 96 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 96 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 6.458% | 25.83% | [6 empty] | 21.43% | 85.71% | [6 empty] | 12.5% | 50% |  | 6.042% | 0 |  |  |  | 97 | 0.4 | 0.11667 | [80 empty] | -8.929% | 0 |  |  |  | 97 | 0.60714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 97 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 85.71% | [5 empty] | 42.86% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 98 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 98 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-15 | 2026-06-15 | 1 | 98 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 51.67% | [5 empty] | 25.83% |  | 85.71% | [5 empty] | 42.86% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 99 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 99 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 25.83% | 51.67% | [6 empty] | 42.86% | 85.71% | [6 empty] | 5% | 10% |  | -20.83% | 0 |  |  |  | 100 | 0.4 | 0.11667 | [80 empty] | -37.86% | 0 |  |  |  | 100 | 0.60714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 85.71% | [5 empty] | 21.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 101 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 101 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 51.67% | [5 empty] | 12.92% |  | 85.71% | [5 empty] | 21.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 102 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 102 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 103 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 103 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 85.71% | [5 empty] | 8.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 104 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 104 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 85.71% | [5 empty] | 8.571% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 105 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 105 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 105 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 51.67% | [5 empty] | 5.167% |  | 85.71% | [5 empty] | 8.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 106 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 106 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 5.167% | 51.67% | [6 empty] | 8.571% | 85.71% | [6 empty] | 6% | 60% |  | 0.8333% | 0 |  |  |  | 107 | 0.4 | 0.11667 | [80 empty] | -2.571% | 0 |  |  |  | 107 | 0.60714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 107 | 0.33333 | 0.16667
|  |  |  | AreaOwner 1 KOM PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 108 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 108 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-21 | 2026-05-21 | 1 | 108 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.3 |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 109 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 109 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 109 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM Indorama |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 110 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 110 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-11 | 2026-06-11 | 1 | 110 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 Training Indorama |  |  | 1 | NOS |  |  |  |  | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 111 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 111 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 |  |  | 1 | [5 empty] | 20% |  | 51.67% | [5 empty] | 10.33% |  | 85.71% | [5 empty] | 17.14% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 112 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 112 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 51.67% | [5 empty] | 0% |  | 85.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-05-18 | 2026-07-16 | 60 | 113 | 0.4 | 0.11667 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-25 | 2026-06-21 | 28 | 113 | 0.60714 | 0.25 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-07-12 | 2026-07-31 | 20 | 114 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.6% | 47.8% | 26.8% | 3.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-06-22 | 2026-07-12 | 21 | 114 |  |  | 0% | 0% | 0% | 0% | 0% | 16.14% | 37.67% | 43.78% | 2.413% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 114 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 115 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 115 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-21 | 10 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-01 | 10 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-21 | 10 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-01 | 10 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 118 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 118 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-02 | 2026-07-03 | 2 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-02 | 2026-07-03 | 2 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-22 | 2026-07-23 | 2 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-02 | 2026-07-03 | 2 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 122 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 122 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-31 | 8 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-04 | 2026-07-06 | 3 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-31 | 8 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-04 | 2026-07-06 | 3 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 125 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 125 | 0 | 0 | [80 empty] | 0 |  |  |  | 125 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 126 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 126 |  |  | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 126 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 128 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-12 | 2026-07-31 | 20 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.35 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-07-12 | 21 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-24 | 2026-07-31 | 8 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-04 | 2026-07-12 | 9 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0.44444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 134 | [87 empty] | 134 | [86 empty] | 134
[44 empty] | 135 | [87 empty] | 135 | [86 empty] | 135
C | [8 empty] | 20% | 100% | [6 empty] | 1.138% | 5.688% |  |  | 1.138% | 0% |  |  | 3.4% | 17% |  |  | 3.4% | 0% |  |  | 1.807% | 9.035% |  |  | 1.695% | 0.112% | 0.6695% |  | 2026-06-05 | 2026-08-26 | 83 | 136 |  |  | 0% | 0% | 0% | 0.6% | 1.3% | 2% | 2.7% | 3.4% | 4.1% | 5.735% | 8.617% | 14.3% | 18.56% | 19.44% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | -1.593% |  | 2026-06-01 | 2026-07-31 | 61 | 136 |  |  | 0% | 0% | 0.6% | 2% | 3.4% | 4.8% | 6% | 7.132% | 11.09% | 16.48% | 19.69% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |  | 2026-05-21 | 2026-06-20 | 31 | 136 |  |  | 0% | 0.1969% | 0.3609% | 1.132% | 1.807% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077%
3 | C1/2 | RC040221 | Amata City Reducing Station | [6 empty] | 50% | 100% | [6 empty] | 2.844% | 5.688% | [6 empty] | 8.5% | 17% | [6 empty] | 3.655% | 7.31% |  |  |  | 0.8112% |  |  |  |  | 137 |  |  | 0% | 0% | 0% | 1.5% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 6.425% | 12.66% | 16.27% | 2.8% | 1.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.845% |  |  |  |  | 137 |  |  | 0% | 0% | 1.5% | 3.5% | 3.5% | 3.5% | 3% | 2.412% | 8.44% | 8.44% | 14.28% | 1.424% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 137 |  |  | 0% | 0.6094% | 0.8203% | 1.4% | 0.825% | 1.35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 5.688% | 18.96% | [6 empty] | 17% | 56.67% | [6 empty] | 6.75% | 22.5% |  |  | 1.063% | 1 | 2026-06-05 | 2026-08-03 | 60 | 138 |  |  | 0% | 0% | 0% | 10% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -10.25% | 1 | 2026-06-01 | 2026-06-30 | 30 | 138 |  |  | 0% | 0% | 10% | 23.33% | 23.33% | 23.33% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.315 | 2026-05-21 | 2026-06-20 | 31 | 138 |  |  | 0% | 4.062% | 5.469% | 8.802% | 4.167% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 3.25% | 21.67% | [6 empty] | 8.5% | 56.67% | [6 empty] | 0% | 0% |  | -3.25% | 0 |  |  |  | 139 | 0.1 | 0.11667 | [80 empty] | -8.5% | 0 |  |  |  | 139 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 139 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 21.67% | [5 empty] | 13% |  | 56.67% | [5 empty] | 34% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 140 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 140 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-20 | 2026-06-20 | 1 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 21.67% | [5 empty] | 8.667% |  | 56.67% | [5 empty] | 22.67% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 141 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 141 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 2.708% | 10.83% | [6 empty] | 14.17% | 56.67% | [6 empty] | 12.5% | 50% |  | 9.792% | 0 |  |  |  | 142 | 0.1 | 0.11667 | [80 empty] | -1.667% | 0 |  |  |  | 142 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 142 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 21.67% | [5 empty] | 10.83% |  | 56.67% | [5 empty] | 28.33% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 143 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 143 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-26 | 2026-06-10 | 16 | 143 | 1 | 0 | 0 | 0.125 | 0.4375 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 21.67% | [5 empty] | 10.83% |  | 56.67% | [5 empty] | 28.33% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 144 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 144 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 10.83% | 21.67% | [6 empty] | 28.33% | 56.67% | [6 empty] | 5% | 10% |  | -5.833% | 0 |  |  |  | 145 | 0.1 | 0.11667 | [80 empty] | -23.33% | 0 |  |  |  | 145 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 145 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 146 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 146 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 147 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 147 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 21.67% | [5 empty] | 4.333% |  | 56.67% | [5 empty] | 11.33% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 148 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 148 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 149 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 149 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 150 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 150 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 150 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 151 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 151 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 2.167% | 21.67% | [6 empty] | 5.667% | 56.67% | [6 empty] | 5% | 50% |  | 2.833% | 0 |  |  |  | 152 | 0.1 | 0.11667 | [80 empty] | -0.6667% | 0 |  |  |  | 152 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 152 | 0.33333 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 153 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 153 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-21 | 2026-05-21 | 1 | 153 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.3 |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 154 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 154 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 154 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM Amata |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 155 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 155 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 |  |  | 1 | [5 empty] | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 156 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 156 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 21.67% | [5 empty] | 0% |  | 56.67% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 157 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 157 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 21.67% | [5 empty] | 0% |  | 56.67% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 158 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 158 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-07-20 | 2026-08-16 | 28 | 159 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.36% | 31.17% | 42.9% | 8% | 4.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-07-07 | 2026-07-31 | 25 | 159 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.89% | 24.12% | 24.12% | 40.81% | 4.069% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 159 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 160 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 160 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-20 | 2026-07-31 | 12 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.58333 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-22 | 16 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.4375 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-20 | 2026-07-31 | 12 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.58333 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-22 | 16 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.4375 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 163 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 163 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-01 | 2026-08-02 | 2 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-23 | 2026-07-24 | 2 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-01 | 2026-08-02 | 2 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-23 | 2026-07-24 | 2 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-01 | 2026-08-02 | 2 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-23 | 2026-07-24 | 2 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 167 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 167 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-08-16 | 14 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-25 | 2026-07-31 | 7 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-08-16 | 14 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-25 | 2026-07-31 | 7 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 170 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 170 | 0 | 0 | [80 empty] | 0 |  |  |  | 170 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 171 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 171 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 171 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 173 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-20 | 2026-08-16 | 28 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-31 | 25 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.28 | 0.28 | 0.28 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-08-16 | 14 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21429 | 0.5 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-25 | 2026-07-31 | 7 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 179 | [87 empty] | 179 | [86 empty] | 179
3 | C2/2 | RC04011 | Bangkok Polyester Public Co., Ltd. | [6 empty] | 50% | 100% | [6 empty] | 2.844% | 5.688% | [6 empty] | 8.5% | 17% | [6 empty] | 5.38% | 10.76% |  |  |  | 2.536% |  |  |  |  | 180 |  |  | 0% | 0% | 0% | 1.5% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 12.16% | 18.49% | 2.8% | 2.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.12% |  |  |  |  | 180 |  |  | 0% | 0% | 1.5% | 3.5% | 3.5% | 3.5% | 3% | 3.246% | 11.36% | 18.49% | 1.777% | 0.1273% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 180 |  |  | 0% | 0.375% | 0% | 2.455% | 2.55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 5.688% | 18.96% | [6 empty] | 17% | 56.67% | [6 empty] | 10.2% | 34% |  |  | 4.513% | 1 | 2026-06-05 | 2026-08-03 | 60 | 181 |  |  | 0% | 0% | 0% | 10% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6.8% | 1 | 2026-06-01 | 2026-06-30 | 30 | 181 |  |  | 0% | 0% | 10% | 23.33% | 23.33% | 23.33% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.34 | 2026-05-21 | 2026-06-17 | 28 | 181 |  |  | 0% | 2.5% | 0% | 15.83% | 15.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 3.25% | 21.67% | [6 empty] | 8.5% | 56.67% | [6 empty] | 9% | 60% |  | 5.75% | 0 |  |  |  | 182 | 0.1 | 0.11667 | [80 empty] | 0.5% | 0 |  |  |  | 182 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 182 | 0 | 0.5
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 21.67% | [5 empty] | 13% |  | 56.67% | [5 empty] | 34% |  | 100% | [5 empty] | 60% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 183 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 183 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-17 | 2026-06-17 | 1 | 183 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 21.67% | [5 empty] | 8.667% |  | 56.67% | [5 empty] | 22.67% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 184 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 184 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 2.708% | 10.83% | [6 empty] | 14.17% | 56.67% | [6 empty] | 12.5% | 50% |  | 9.792% | 0 |  |  |  | 185 | 0.1 | 0.11667 | [80 empty] | -1.667% | 0 |  |  |  | 185 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 185 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 21.67% | [5 empty] | 10.83% |  | 56.67% | [5 empty] | 28.33% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 186 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 186 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-05 | 2026-06-05 | 1 | 186 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 21.67% | [5 empty] | 10.83% |  | 56.67% | [5 empty] | 28.33% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 187 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 187 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 10.83% | 21.67% | [6 empty] | 28.33% | 56.67% | [6 empty] | 5% | 10% |  | -5.833% | 0 |  |  |  | 188 | 0.1 | 0.11667 | [80 empty] | -23.33% | 0 |  |  |  | 188 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 188 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 189 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 189 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 190 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 190 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 21.67% | [5 empty] | 4.333% |  | 56.67% | [5 empty] | 11.33% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 191 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 191 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 192 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 192 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 193 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 193 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 193 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 21.67% | [5 empty] | 2.167% |  | 56.67% | [5 empty] | 5.667% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 194 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 194 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 2.167% | 21.67% | [6 empty] | 5.667% | 56.67% | [6 empty] | 7.5% | 75% |  | 5.333% | 0 |  |  |  | 195 | 0.1 | 0.11667 | [80 empty] | 1.833% | 0 |  |  |  | 195 | 0.33333 | 0.23333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 195 | 0.33333 | 0.16667
|  |  |  | AreaOwner 1 KOM PTTRG.3 |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 196 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 196 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-21 | 2026-05-21 | 1 | 196 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.3 |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 197 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 197 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 197 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 CSR หนองบอน |  |  | 1 | NOS |  |  |  |  | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 198 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 198 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-16 | 2026-06-16 | 1 | 198 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 |  |  | 1 | [5 empty] | 25% |  | 21.67% | [5 empty] | 5.417% |  | 56.67% | [5 empty] | 14.17% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 199 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 199 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 21.67% | [5 empty] | 0% |  | 56.67% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 200 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 200 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 21.67% | [5 empty] | 0% |  | 56.67% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-05 | 2026-08-03 | 60 | 201 | 0.1 | 0.11667 | 0 | 0 | 0 | 0.1 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-01 | 2026-06-30 | 30 | 201 | 0.33333 | 0.23333 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-07-30 | 2026-08-26 | 28 | 202 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.17% | 52.83% | 8% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-07-07 | 2026-07-31 | 25 | 202 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.275% | 32.46% | 52.82% | 5.077% | 0.3636% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 202 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 203 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 203 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-30 | 2026-08-10 | 12 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-18 | 12 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.58333 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-30 | 2026-08-10 | 12 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-18 | 12 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.58333 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 206 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 206 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-11 | 2026-08-12 | 2 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-19 | 2026-07-20 | 2 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-11 | 2026-08-12 | 2 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-19 | 2026-07-20 | 2 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-11 | 2026-08-12 | 2 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-19 | 2026-07-20 | 2 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 210 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 210 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-13 | 2026-08-26 | 14 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-21 | 2026-07-23 | 3 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-13 | 2026-08-26 | 14 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-21 | 2026-07-23 | 3 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 213 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 213 | 0 | 0 | [80 empty] | 0 |  |  |  | 213 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 214 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 214 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 214 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 216 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-30 | 2026-08-26 | 28 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-07 | 2026-07-23 | 17 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11765 | 0.41176 | 0.41176 | 0.058824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-13 | 2026-08-26 | 14 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-21 | 2026-07-31 | 11 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.63636 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 222 | [87 empty] | 222 | [86 empty] | 222
[44 empty] | 223 | [87 empty] | 223 | [86 empty] | 223
D | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% |  |  | 0% | 0% |  |  | 2.143% | 10.71% |  |  | 2.143% | 0% |  |  | 1.512% | 7.56% |  |  | 1.4% | 0.112% | 1.512% |  | 2026-06-19 | 2026-10-08 | 112 | 224 |  |  | 0% | 0% | 0% | 0% | 0% | 0.3214% | 0.6964% | 1.071% | 1.446% | 1.821% | 2.196% | 2.571% | 2.946% | 3.321% | 4.197% | 7.826% | 12.52% | 17.22% | 18.57% | 19.57% | 19.95% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | -0.6309% |  | 2026-06-08 | 2026-08-23 | 77 | 224 |  |  | 0% | 0% | 0% | 0.6429% | 2.143% | 3.643% | 5.143% | 6% | 6% | 6% | 7.055% | 10.75% | 15.86% | 19.3% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |  | 2026-05-27 | 2026-06-15 | 20 | 224 |  |  | 0% | 0.05% | 0.575% | 1.182% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512% | 1.512%
1 | D1/2 | RC044041 | Esso (Thailand) Public Co., Ltd. | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 5.357% | 10.71% | [6 empty] | 3.905% | 7.81% |  |  |  | 3.905% |  |  |  |  | 225 |  |  | 0% | 0% | 0% | 0% | 0% | 0.8036% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 3.441% | 9.698% | 13.78% | 8.356% | 3.369% | 1.98% | 0.9375% | 0.1339% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.452% |  |  |  |  | 225 |  |  | 0% | 0% | 0% | 1.607% | 3.75% | 3.75% | 3.75% | 2.143% | 0% | 0% | 2.152% | 7.531% | 7.531% | 14.9% | 2.881% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 225 |  |  | 0% | 0.125% | 1.375% | 1.58% | 0.825% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 10.71% | 35.71% | [6 empty] | 7.25% | 24.17% |  |  | 7.25% | 1 | 2026-06-19 | 2026-10-08 | 112 | 226 |  |  | 0% | 0% | 0% | 0% | 0% | 5.357% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 0.8929% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.464% | 1 | 2026-06-08 | 2026-07-05 | 28 | 226 |  |  | 0% | 0% | 0% | 10.71% | 25% | 25% | 25% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.24167 | 2026-05-27 | 2026-06-15 | 20 | 226 |  |  | 0% | 0.8333% | 9.167% | 10% | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 0% | 0% | [6 empty] | 5.357% | 35.71% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 227 | 0 | 0 | [80 empty] | -5.357% | 0 |  |  |  | 227 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 227 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 21.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 228 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 14.29% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 229 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 0% | 0% | [6 empty] | 8.929% | 35.71% | [6 empty] | 12.5% | 50% |  | 12.5% | 0 |  |  |  | 230 | 0 | 0 | [80 empty] | 3.571% | 0 |  |  |  | 230 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 230 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 17.86% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 231 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-27 | 2026-06-10 | 15 | 231 | 1 | 0 | 0 | 0.066667 | 0.46667 | 0.46667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 17.86% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 232 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 17.86% | 35.71% | [6 empty] | 5% | 10% |  | 5% | 0 |  |  |  | 233 | 0 | 0 | [80 empty] | -12.86% | 0 |  |  |  | 233 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 233 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 234 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 235 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 7.143% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 236 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 237 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 238 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 238 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 239 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 3.571% | 35.71% | [6 empty] | 6.667% | 66.67% |  | 6.667% | 0 |  |  |  | 240 | 0 | 0 | [80 empty] | 3.095% | 0 |  |  |  | 240 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 240 | 0.33333 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.1 |  |  | 1 | NOS |  |  |  |  | 33.33% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 11.9% |  | 100% | [5 empty] | 33.33% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 241 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-28 | 2026-05-28 | 1 | 241 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.1 |  |  | 1 | NOS |  |  |  |  | 33.33% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 11.9% |  | 100% | [5 empty] | 33.33% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 242 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 242 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 |  |  | 1 | NOS |  |  |  |  | 33.33% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 11.9% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 243 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 244 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 245 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 246 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-08-25 | 2026-09-26 | 33 | 247 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.152% | 25.03% | 36.7% | 21.2% | 6.947% | 2.977% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-07-28 | 2026-08-23 | 27 | 247 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.148% | 21.52% | 21.52% | 42.58% | 8.233% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 247 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 248 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 248 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-25 | 2026-09-08 | 15 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13333 | 0.46667 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-14 | 18 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11111 | 0.38889 | 0.38889 | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-25 | 2026-09-08 | 15 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13333 | 0.46667 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-14 | 18 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11111 | 0.38889 | 0.38889 | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 251 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 251 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-09 | 2026-09-10 | 2 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-15 | 2026-08-16 | 2 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-09 | 2026-09-10 | 2 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-15 | 2026-08-16 | 2 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-09 | 2026-09-10 | 2 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-15 | 2026-08-16 | 2 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 255 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 255 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-11 | 2026-09-26 | 16 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.375 | 0.4375 | 0.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-08-23 | 7 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-11 | 2026-09-26 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.375 | 0.4375 | 0.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-08-23 | 7 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 258 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 258 | 0 | 0 | [80 empty] | 0 |  |  |  | 258 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 259 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 259 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 259 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 261 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-25 | 2026-09-26 | 33 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-11 | 2026-09-26 | 16 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.375 | 0.4375 | 0.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-18 | 2026-08-23 | 6 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 267 | [87 empty] | 267 | [86 empty] | 267
1 | D2/2 | RC044043 | Laem Chabang Industrial Estate | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 5.357% | 10.71% | [6 empty] | 3.655% | 7.31% |  |  |  | 3.655% |  |  |  |  | 268 |  |  | 0% | 0% | 0% | 0% | 0% | 0.8036% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 0.9375% | 8.447% | 9.698% | 15.15% | 3.369% | 3.022% | 0.9375% | 0.1339% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.702% |  |  |  |  | 268 |  |  | 0% | 0% | 0% | 1.607% | 3.75% | 3.75% | 3.75% | 2.143% | 0% | 0% | 3.124% | 10.93% | 18.04% | 2.27% | 0.6302% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 268 |  |  | 0% | 0.125% | 1.25% | 1.455% | 0.825% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 10.71% | 35.71% | [6 empty] | 6.75% | 22.5% |  |  | 6.75% | 1 | 2026-06-19 | 2026-10-08 | 112 | 269 |  |  | 0% | 0% | 0% | 0% | 0% | 5.357% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 0.8929% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.964% | 1 | 2026-06-08 | 2026-07-05 | 28 | 269 |  |  | 0% | 0% | 0% | 10.71% | 25% | 25% | 25% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.225 | 2026-05-27 | 2026-06-15 | 20 | 269 |  |  | 0% | 0.8333% | 8.333% | 9.167% | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 0% | 0% | [6 empty] | 5.357% | 35.71% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 270 | 0 | 0 | [80 empty] | -5.357% | 0 |  |  |  | 270 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 270 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 21.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 271 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 14.29% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 272 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 0% | 0% | [6 empty] | 8.929% | 35.71% | [6 empty] | 12.5% | 50% |  | 12.5% | 0 |  |  |  | 273 | 0 | 0 | [80 empty] | 3.571% | 0 |  |  |  | 273 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 273 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 17.86% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 274 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-27 | 2026-06-10 | 15 | 274 | 1 | 0 | 0 | 0.066667 | 0.46667 | 0.46667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 17.86% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 275 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 17.86% | 35.71% | [6 empty] | 5% | 10% |  | 5% | 0 |  |  |  | 276 | 0 | 0 | [80 empty] | -12.86% | 0 |  |  |  | 276 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 276 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 277 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 278 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 7.143% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 279 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 280 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 281 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 281 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 3.571% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 282 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 3.571% | 35.71% | [6 empty] | 5% | 50% |  | 5% | 0 |  |  |  | 283 | 0 | 0 | [80 empty] | 1.429% | 0 |  |  |  | 283 | 0.10714 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 283 | 0.33333 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.1 |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 284 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-28 | 2026-05-28 | 1 | 284 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.1 |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 285 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 285 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM กนอ กฟผ |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 286 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 |  |  | 1 | [5 empty] | 25% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 8.929% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 287 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 288 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 35.71% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-06-19 | 2026-10-08 | 112 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053571 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0089286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-08 | 2026-07-05 | 28 | 289 | 0.10714 | 0.25 | 0 | 0 | 0 | 0.10714 | 0.25 | 0.25 | 0.25 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-08-28 | 2026-09-29 | 33 | 290 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.45% | 25.03% | 40.61% | 6.947% | 5.955% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-07-28 | 2026-08-23 | 27 | 290 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.926% | 31.24% | 51.55% | 6.484% | 1.801% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 290 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 291 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 291 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-28 | 2026-09-11 | 15 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.46667 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-08 | 12 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.58333 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-28 | 2026-09-11 | 15 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.46667 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-08 | 12 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.58333 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 294 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 294 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-12 | 2026-09-13 | 2 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-09 | 2026-08-10 | 2 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-12 | 2026-09-13 | 2 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-09 | 2026-08-10 | 2 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-12 | 2026-09-13 | 2 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-09 | 2026-08-10 | 2 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 298 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 298 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-14 | 2026-09-29 | 16 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1875 | 0.4375 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-11 | 2026-08-13 | 3 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-14 | 2026-09-29 | 16 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1875 | 0.4375 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-11 | 2026-08-13 | 3 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 301 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 301 | 0 | 0 | [80 empty] | 0 |  |  |  | 301 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 302 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 302 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 302 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 304 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-28 | 2026-09-29 | 33 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.21212 | 0.21212 | 0.21212 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-07-28 | 2026-08-23 | 27 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074074 | 0.25926 | 0.25926 | 0.25926 | 0.14815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-14 | 2026-09-29 | 16 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1875 | 0.4375 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-11 | 2026-08-23 | 13 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15385 | 0.53846 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 310 | [87 empty] | 310 | [86 empty] | 310
[44 empty] | 311 | [87 empty] | 311 | [86 empty] | 311
E | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% |  |  | 0% | 0% |  |  | 15.21% | 76.07% |  |  | 6% | 9.215% |  |  | 3.372% | 16.86% |  |  | 3.26% | 0.112% | 3.372% |  | 2026-08-03 | 2026-10-28 | 87 | 312 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3% | 1% | 1.7% | 2.4% | 3.1% | 3.8% | 4.5% | 5.2% | 8.199% | 11.76% | 16.92% | 19.44% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | -11.84% |  | 2026-05-18 | 2026-06-29 | 43 | 312 |  |  | 0.8571% | 2.857% | 5.913% | 10.75% | 15.21% | 19.25% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |  | 2026-05-20 | 2026-06-20 | 32 | 312 |  |  | 0.475% | 0.725% | 1% | 1.527% | 3.372% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927% | 3.927%
1 | E1/2 | RC0631100003 | Loyal Haieleung Copper (Thailand) Co., Ltd. | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 34.1% | 68.2% | [6 empty] | 9.43% | 18.86% |  |  |  | 9.43% |  |  |  |  | 313 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 12.68% | 8.268% | 11.23% | 4.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -24.67% |  |  |  |  | 313 |  |  | 2.143% | 5% | 7.387% | 11.21% | 8.356% | 12.96% | 2.938% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 313 |  |  | 0% | 1.25% | 1.375% | 0.58% | 6.225% | 0.45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 30% | 100% | [6 empty] | 18.3% | 61% |  |  | 18.3% | 1 | 2026-08-03 | 2026-10-01 | 60 | 314 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 1.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -11.7% | 1 | 2026-05-18 | 2026-06-07 | 21 | 314 |  |  | 14.29% | 33.33% | 33.33% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.64 | 2026-05-26 | 2026-06-20 | 26 | 314 |  |  | 0% | 8.333% | 9.167% | 3.333% | 40.17% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 0% | 0% | [6 empty] | 15% | 100% | [6 empty] | 9% | 60% |  | 9% | 0 |  |  |  | 315 | 0 | 0 | [80 empty] | -6% | 0 |  |  |  | 315 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 315 | 0 | 0.5
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 60% |  | 100% | [5 empty] | 60% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 316 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-13 | 2026-06-13 | 1 | 316 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 317 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 0% | 0% | [6 empty] | 25% | 100% | [6 empty] | 25% | 100% |  | 25% | 0 |  |  |  | 318 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 318 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 318 | 0 | 1
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 50% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 319 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-26 | 2026-05-28 | 3 | 319 | 1 | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 50% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 320 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-17 | 2026-06-17 | 1 | 320 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 50% | 100% | [6 empty] | 19.5% | 39% |  | 19.5% | 0 |  |  |  | 321 | 0 | 0 | [80 empty] | -30.5% | 0 |  |  |  | 321 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 321 | 0.027778 | 0.37222
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 322 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-13 | 2026-06-13 | 1 | 322 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 323 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 324 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 40% | [5 empty] | 4% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 325 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-16 | 2026-06-20 | 5 | 325 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 326 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 326 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 327 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 10% | 100% | [6 empty] | 7.5% | 75% |  | 7.5% | 0 |  |  |  | 328 | 0 | 0 | [80 empty] | -2.5% | 0 |  |  |  | 328 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 328 | 0.5 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.1 |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 329 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-28 | 2026-05-28 | 1 | 329 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.1 |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 330 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 330 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM LHCT |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 331 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-02 | 2026-06-02 | 1 | 331 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 |  |  | 1 | [5 empty] | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 332 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 333 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 334 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 38.2% | 54.57% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-09-24 | 2026-10-20 | 27 | 335 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.24% | 22.91% | 32.07% | 13.78% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -37.64% | 1 | 2026-06-02 | 2026-06-29 | 28 | 335 |  |  | 0% | 0% | 6.821% | 23.88% | 23.88% | 37.04% | 8.393% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 335 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 336 | 0 | 0 | [80 empty] | -50% | 0 |  |  |  | 336 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 336 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 70% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-05 | 12 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-17 | 16 | 337 | 0.5625 | 0.4375 | 0 | 0 | 0.125 | 0.4375 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 30% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-05 | 12 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-17 | 16 | 338 | 0.5625 | 0.4375 | 0 | 0 | 0.125 | 0.4375 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 339 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 339 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-13 | 2026-10-14 | 2 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-18 | 2026-06-21 | 4 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-13 | 2026-10-14 | 2 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-18 | 2026-06-21 | 4 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-13 | 2026-10-14 | 2 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-18 | 2026-06-21 | 4 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 343 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 343 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-15 | 2026-10-20 | 6 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-06-28 | 7 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-15 | 2026-10-20 | 6 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-06-28 | 7 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 4.571% | 45.71% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 346 | 0 | 0 | [80 empty] | -3.771% | 0 |  |  |  | 346 | 0.27551 | 0.21429 | [80 empty] | 0 |  |  |  | 346 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 11.43% | 57.14% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 347 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 347 |  |  | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 347 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 22.86% |  | 0% | [5 empty] | 0% |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 348 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 22.86% |  | 100% | [5 empty] | 40% |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 349 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 349 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 350 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 351 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 352 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-20 | 27 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25926 | 0.25926 | 0.25926 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 353 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-15 | 2026-10-20 | 6 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-22 | 2026-06-29 | 8 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.375 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 355 | [87 empty] | 355 | [86 empty] | 355
5 | E2/2 | RC410101 | Gangwal Textile Co., Ltd. | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 41.97% | 83.95% | [6 empty] | 7.43% | 14.86% |  |  |  | 7.43% |  |  |  |  | 356 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 2.31% | 9.56% | 14.56% | 7.748% | 2.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -34.54% |  |  |  |  | 356 |  |  | 2.143% | 5% | 7.892% | 12.98% | 13.96% | 7.207% | 0.8182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 356 |  |  | 2.375% | 0% | 0% | 2.055% | 3% | 2.325% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 30% | 100% | [6 empty] | 14.3% | 47.67% |  |  | 14.3% | 1 | 2026-08-03 | 2026-10-01 | 60 | 357 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 11.67% | 1.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -15.7% | 1 | 2026-05-18 | 2026-06-07 | 21 | 357 |  |  | 14.29% | 33.33% | 33.33% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.63167 | 2026-05-20 | 2026-06-20 | 32 | 357 |  |  | 15.83% | 0% | 0% | 13.17% | 18.67% | 15.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 0% | 0% | [6 empty] | 15% | 100% | [6 empty] | 9% | 60% |  | 9% | 0 |  |  |  | 358 | 0 | 0 | [80 empty] | -6% | 0 |  |  |  | 358 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 358 | 0.5 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 60% |  | 100% | [5 empty] | 60% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 359 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-06 | 2026-06-06 | 1 | 359 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 360 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 0% | 0% | [6 empty] | 25% | 100% | [6 empty] | 12.5% | 50% |  | 12.5% | 0 |  |  |  | 361 | 0 | 0 | [80 empty] | -12.5% | 0 |  |  |  | 361 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 361 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 50% |  | 100% | [5 empty] | 50% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 362 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-20 | 2026-05-20 | 1 | 362 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 50% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 363 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-18 | 2026-06-18 | 1 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 50% | 100% | [6 empty] | 19.5% | 39% |  | 19.5% | 0 |  |  |  | 364 | 0 | 0 | [80 empty] | -30.5% | 0 |  |  |  | 364 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 364 | 0.027778 | 0.37222
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 100% | [5 empty] | 25% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 365 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-13 | 2026-06-13 | 1 | 365 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 25% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 366 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 367 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 40% | [5 empty] | 4% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 368 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-16 | 2026-06-20 | 5 | 368 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 369 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 369 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 10% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 370 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 10% | 100% | [6 empty] | 6.667% | 66.67% |  | 6.667% | 0 |  |  |  | 371 | 0 | 0 | [80 empty] | -3.333% | 0 |  |  |  | 371 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 371 | 0.33333 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.5 |  |  | 1 | NOS |  |  |  |  | 33.33% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 33.33% |  | 100% | [5 empty] | 33.33% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 372 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-20 | 2026-05-20 | 1 | 372 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.5 |  |  | 1 | NOS |  |  |  |  | 33.33% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 33.33% |  | 100% | [5 empty] | 33.33% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 373 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-08 | 2026-06-08 | 1 | 373 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 |  |  | 1 | [5 empty] | 33.33% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 33.33% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 374 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 375 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 376 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-08-03 | 2026-10-01 | 60 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.11667 | 0.016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-07 | 21 | 377 | 1 | 0 | 0.14286 | 0.33333 | 0.33333 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 53.95% | 77.07% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-10-02 | 2026-10-28 | 27 | 378 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.6% | 26.6% | 41.6% | 22.14% | 8.062% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -53.39% | 1 | 2026-06-02 | 2026-06-29 | 28 | 378 |  |  | 0% | 0% | 8.264% | 28.92% | 39.88% | 20.59% | 2.338% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 378 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 50% | 100% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 379 | 0 | 0 | [80 empty] | -50% | 0 |  |  |  | 379 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 379 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 70% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-02 | 2026-10-13 | 12 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-14 | 13 | 380 | 0.69231 | 0.30769 | 0 | 0 | 0.15385 | 0.53846 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 30% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-02 | 2026-10-13 | 12 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-14 | 13 | 381 | 0.69231 | 0.30769 | 0 | 0 | 0.15385 | 0.53846 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 22.5% | 75% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 382 | 0 | 0 | [80 empty] | -22.5% | 0 |  |  |  | 382 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 382 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 75% | [5 empty] | 30% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-14 | 2026-10-15 | 2 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-15 | 2026-06-18 | 4 | 383 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 75% | [5 empty] | 22.5% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-14 | 2026-10-15 | 2 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-15 | 2026-06-18 | 4 | 384 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 75% | [5 empty] | 22.5% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-14 | 2026-10-15 | 2 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-15 | 2026-06-18 | 4 | 385 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 386 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 386 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-16 | 2026-10-28 | 13 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46154 | 0.53846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-19 | 2026-06-23 | 5 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-16 | 2026-10-28 | 13 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46154 | 0.53846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-19 | 2026-06-23 | 5 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 4.571% | 45.71% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 389 | 0 | 0 | [80 empty] | -3.771% | 0 |  |  |  | 389 | 0.27551 | 0.21429 | [80 empty] | 0 |  |  |  | 389 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 11.43% | 57.14% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 390 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 390 |  |  | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 390 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 22.86% |  | 0% | [5 empty] | 0% |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 391 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 22.86% |  | 100% | [5 empty] | 40% |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 392 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 392 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 393 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 394 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 395 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 57.14% | [5 empty] | 11.43% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-09-24 | 2026-10-28 | 35 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-02 | 2026-06-29 | 28 | 396 | 0.32143 | 0.25 | 0 | 0 | 0.071429 | 0.25 | 0.25 | 0.25 | 0.17857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-16 | 2026-10-28 | 13 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46154 | 0.53846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-06-19 | 2026-06-29 | 11 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54545 | 0.45455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 398 | [87 empty] | 398 | [86 empty] | 398
[44 empty] | 399 | [87 empty] | 399 | [86 empty] | 399
F | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% |  |  | 0% | 0% |  |  | 2.114% | 21.14% |  |  | 2.114% | 0% |  |  | 0.6176% | 6.176% |  |  | 0.5616% | 0.056% | 0.6176% |  | 2026-07-13 | 2026-11-21 | 132 | 400 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.07826% | 0.2609% | 0.4435% | 0.6261% | 0.8087% | 0.9913% | 1.174% | 1.357% | 1.539% | 1.722% | 1.904% | 2.087% | 2.27% | 2.452% | 3.305% | 5.834% | 8.998% | 9.41% | 9.823% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | -1.496% |  | 2026-05-18 | 2026-09-15 | 121 | 400 |  |  | 0.2045% | 0.6818% | 1.159% | 1.636% | 2.114% | 2.591% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 4.223% | 7.737% | 9.662% | 9.844% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 2026-05-19 | 2026-06-19 | 32 | 400 |  |  | 0.08344% | 0.1655% | 0.2475% | 0.3705% | 0.6176% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641% | 0.641%
2 | F1/1 | RC06611 | The Union Mosaic Industry Co., Ltd. | [6 empty] | 100% | 100% | [6 empty] | 0% | 0% | [6 empty] | 21.14% | 21.14% | [6 empty] | 6.176% | 6.176% |  |  |  | 6.176% |  |  |  |  | 401 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 1.826% | 8.529% | 25.29% | 31.64% | 4.128% | 4.128% | 1.769% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -14.96% |  |  |  |  | 401 |  |  | 2.045% | 4.773% | 4.773% | 4.773% | 4.773% | 4.773% | 4.091% | 0% | 0% | 0% | 0% | 0% | 0% | 12.23% | 35.14% | 19.25% | 1.822% | 1.562% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 401 |  |  | 0.8344% | 0.8203% | 0.8203% | 1.23% | 2.47% | 0.2344% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Engineering | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 21.14% | 70.45% | [6 empty] | 5.616% | 18.72% |  |  | 5.616% | 1 | 2026-07-13 | 2026-11-04 | 115 | 402 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.609% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 6.087% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -15.52% | 1 | 2026-05-18 | 2026-06-30 | 44 | 402 |  |  | 6.818% | 15.91% | 15.91% | 15.91% | 15.91% | 15.91% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.195 | 2026-05-19 | 2026-06-19 | 32 | 402 |  |  | 2.781% | 2.734% | 2.734% | 3.568% | 6.901% | 0.7812% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Boring log | [8 empty] | 15% | 100% | [6 empty] | 0% | 0% | [6 empty] | 10.57% | 70.45% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 403 | 0 | 0 | [80 empty] | -10.57% | 0 |  |  |  | 403 | 0.54545 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 403 | 0 | 0
|  |  |  | Boring log |  |  | 1 | NOS |  |  |  |  | 60% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 42.27% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 404 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Report |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 28.18% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 405 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Survay and Verify | [8 empty] | 25% | 100% | [6 empty] | 0% | 0% | [6 empty] | 17.61% | 70.45% | [6 empty] | 11.72% | 46.88% |  | 11.72% | 0 |  |  |  | 406 | 0 | 0 | [80 empty] | -5.895% | 0 |  |  |  | 406 | 0.54545 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 406 | 0 | 0
|  |  |  | Site servay |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 35.23% |  | 93.75% | [5 empty] | 46.88% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 407 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-19 | 2026-06-19 | 32 | 407 | 0.71875 | 0.21875 | 0.0625 | 0.21875 | 0.21875 | 0.21875 | 0.21875 | 0.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Verify |  |  | 1 | NOS |  |  |  |  | 50% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 35.23% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 408 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Engineering Doc | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 35.23% | 70.45% | [6 empty] | 5% | 10% |  | 5% | 0 |  |  |  | 409 | 0 | 0 | [80 empty] | -30.23% | 0 |  |  |  | 409 | 0.54545 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 409 | 0.027778 | 0.13889
|  |  |  | Draft Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 17.61% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 410 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Drawing |  |  | 1 | NOS |  |  |  |  | 25% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 17.61% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 411 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Calculation |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 412 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JMS |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 7.045% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 413 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | JSEA |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 7.045% |  | 100% | [5 empty] | 10% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 414 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-10 | 2026-06-15 | 6 | 414 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Emergency Plan |  |  | 1 | NOS |  |  |  |  | 10% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 7.045% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 415 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Permit | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 7.045% | 70.45% | [6 empty] | 2% | 20% |  | 2% | 0 |  |  |  | 416 | 0 | 0 | [80 empty] | -5.045% | 0 |  |  |  | 416 | 0.54545 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 416 | 0.16667 | 0
|  |  |  | AreaOwner 1 KOM PTTRG.2 |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 100% | [5 empty] | 20% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 417 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-05-19 | 2026-05-19 | 1 | 417 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 2 Training RG.2 |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 418 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 3 KOM ทช. |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 419 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 4 KOM ชป. |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 420 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 5 |  |  | 1 | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 14.09% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 421 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AreaOwner 6 | [8 empty] | 0% |  | 0% | [5 empty] | 0% |  | 70.45% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-07-13 | 2026-11-04 | 115 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0.06087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-05-18 | 2026-06-30 | 44 | 422 | 0.54545 | 0.15909 | 0.068182 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.15909 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | [8 empty] | 70% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.56% | 0.8% |  |  | 0.56% | 1 | 2026-10-20 | 2026-11-21 | 33 | 423 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.576% | 33.52% | 42.59% | 5.897% | 5.897% | 2.527% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.56% | 1 | 2026-08-17 | 2026-09-15 | 30 | 423 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.47% | 50.2% | 27.5% | 2.604% | 2.232% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.008 | 2026-06-09 | 2026-06-15 | 7 | 423 |  |  | 0% | 0% | 0% | 0.2286% | 0.5714% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Excavation | [8 empty] | 50% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 424 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 424 | 0 | 0
|  |  |  | Excavation |  |  | 1 | NOS |  |  |  |  | 70% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-20 | 2026-10-30 | 11 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.63636 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-08-25 | 9 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Soil Protection |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-20 | 2026-10-30 | 11 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182 | 0.63636 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-08-25 | 9 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Inspection | [8 empty] | 30% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 427 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 427 | 0 | 0
|  |  |  | NDT |  |  | 1 | NOS |  |  |  |  | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-31 | 2026-11-01 | 2 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-26 | 2026-08-27 | 2 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Advance |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-31 | 2026-11-01 | 2 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-26 | 2026-08-27 | 2 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Coating and Wrapping |  |  | 1 | NOS |  |  |  |  | 30% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-31 | 2026-11-01 | 2 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-26 | 2026-08-27 | 2 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Backfill & Re-instate | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% |  | 0% | 0 |  |  |  | 431 | 0 | 0 | [80 empty] | 0% | 0 |  |  |  | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 431 | 0 | 0
|  |  |  | Re-instate | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-11-02 | 2026-11-21 | 20 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.35 | 0.35 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-28 | 2026-09-01 | 5 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Handover | [8 empty] | 50% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-11-02 | 2026-11-21 | 20 | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.35 | 0.35 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-28 | 2026-09-01 | 5 | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Package | [8 empty] | 10% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 0.8% | 8% |  | 0.8% | 0 |  |  |  | 434 | 0 | 0 | [80 empty] | 0.8% | 0 |  |  |  | 434 | 0 | 0 | [80 empty] | 0 |  |  |  | 434 | 0.040816 | 0.10204
|  |  |  | PROJECT GENERAL DOCUMENT | [8 empty] | 20% | 100% | [6 empty] | 0% | 0% | [6 empty] | 0% | 0% | [6 empty] | 8% | 40% |  | 1 |  |  |  | 435 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  | 435 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | 1 | 435 |  |  | 0 | 0 | 0 | 0.11429 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | KOM&MOM RG /AREA OWNER |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | QA/QC Procedure |  | 1 | NOS | [5 empty] | 40% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 100% | [5 empty] | 40% |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-06-09 | 2026-06-15 | 7 | 437 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0.28571 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Handover |  | 1 | NOS | [5 empty] | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DRAWING & DESIGN CALCULATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DATA SHEET AND SPECIFICATION |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PIPELINE DOCUMENT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-10-20 | 2026-11-21 | 33 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060606 | 0.21212 | 0.21212 | 0.21212 | 0.21212 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-17 | 2026-09-15 | 30 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.23333 | 0.23333 | 0.23333 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | INSPECTION REPORT |  |  | 1 | NOS |  |  |  |  | 20% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  | 0% | [5 empty] | 0% |  |  | 1 | 2026-11-02 | 2026-11-21 | 20 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.35 | 0.35 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2026-08-28 | 2026-09-15 | 19 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31579 | 0.36842 | 0.31579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[44 empty] | 443 | [87 empty] | 443 | [86 empty] | 443
[44 empty] | 444 | [87 empty] | 444 | [86 empty] | 444
[44 empty] | 445 | [87 empty] | 445 | [86 empty] | 445
[44 empty] | 446 | [87 empty] | 446 | [86 empty] | 446
[44 empty] | 447 | [87 empty] | 447 | [86 empty] | 447
[44 empty] | 448 | [87 empty] | 448 | [86 empty] | 448
[44 empty] | 449 | [87 empty] | 449 | [86 empty] | 449
[44 empty] | 450 | [87 empty] | 450 | [86 empty] | 450
[44 empty] | 451 | [87 empty] | 451 | [86 empty] | 451
[44 empty] | 452 | [87 empty] | 452 | [86 empty] | 452
[44 empty] | 453 | [87 empty] | 453 | [86 empty] | 453
[44 empty] | 454 | [87 empty] | 454 | [86 empty] | 454
[44 empty] | 455 | [87 empty] | 455 | [86 empty] | 455
[44 empty] | 456 | [87 empty] | 456 | [86 empty] | 456
[44 empty] | 457 | [87 empty] | 457 | [86 empty] | 457
[44 empty] | 458 | [87 empty] | 458 | [86 empty] | 458
[44 empty] | 459 | [87 empty] | 459 | [86 empty] | 459
[44 empty] | 460 | [87 empty] | 460 | [86 empty] | 460
[44 empty] | 461 | [87 empty] | 461 | [86 empty] | 461
[44 empty] | 462 | [87 empty] | 462 | [86 empty] | 462
[44 empty] | 463 | [87 empty] | 463 | [86 empty] | 463
[44 empty] | 464 | [87 empty] | 464 | [86 empty] | 464
[44 empty] | 465 | [87 empty] | 465 | [86 empty] | 465
[44 empty] | 466 | [87 empty] | 466 | [86 empty] | 466
[44 empty] | 467 | [87 empty] | 467 | [86 empty] | 467
[44 empty] | 468 | [87 empty] | 468 | [86 empty] | 468
[44 empty] | 469 | [87 empty] | 469 | [86 empty] | 469
[44 empty] | 470 | [87 empty] | 470 | [86 empty] | 470
[44 empty] | 471 | [87 empty] | 471 | [86 empty] | 471
[44 empty] | 472 | [87 empty] | 472 | [86 empty] | 472
[44 empty] | 473 | [87 empty] | 473 | [86 empty] | 473
[44 empty] | 474 | [87 empty] | 474 | [86 empty] | 474
[44 empty] | 475 | [87 empty] | 475 | [86 empty] | 475
[44 empty] | 476 | [87 empty] | 476 | [86 empty] | 476
[44 empty] | 477 | [87 empty] | 477 | [86 empty] | 477
[44 empty] | 478 | [87 empty] | 478 | [86 empty] | 478
[44 empty] | 479 | [87 empty] | 479 | [86 empty] | 479
[44 empty] | 480 | [87 empty] | 480 | [86 empty] | 480
[44 empty] | 481 | [87 empty] | 481 | [86 empty] | 481
[44 empty] | 482 | [87 empty] | 482 | [86 empty] | 482
[44 empty] | 483 | [87 empty] | 483 | [86 empty] | 483
[44 empty] | 484 | [87 empty] | 484 | [86 empty] | 484
[44 empty] | 485 | [87 empty] | 485 | [86 empty] | 485
[44 empty] | 486 | [87 empty] | 486 | [86 empty] | 486
[44 empty] | 487 | [87 empty] | 487 | [86 empty] | 487
[44 empty] | 488 | [87 empty] | 488 | [86 empty] | 488
[44 empty] | 489 | [87 empty] | 489 | [86 empty] | 489
[44 empty] | 490 | [87 empty] | 490 | [86 empty] | 490
[44 empty] | 491 | [87 empty] | 491 | [86 empty] | 491
[44 empty] | 492 | [87 empty] | 492 | [86 empty] | 492
[44 empty] | 493 | [87 empty] | 493 | [86 empty] | 493
[44 empty] | 494 | [87 empty] | 494 | [86 empty] | 494
[44 empty] | 495 | [87 empty] | 495 | [86 empty] | 495
[44 empty] | 496 | [87 empty] | 496 | [86 empty] | 496
[44 empty] | 497 | [87 empty] | 497 | [86 empty] | 497
[44 empty] | 498 | [87 empty] | 498 | [86 empty] | 498
[44 empty] | 499 | [87 empty] | 499 | [86 empty] | 499
[44 empty] | 500 | [87 empty] | 500 | [86 empty] | 500
[44 empty] | 501 | [87 empty] | 501 | [86 empty] | 501
[44 empty] | 502 | [87 empty] | 502 | [86 empty] | 502
[44 empty] | 503 | [87 empty] | 503 | [86 empty] | 503
[44 empty] | 504 | [87 empty] | 504 | [86 empty] | 504
[44 empty] | 505 | [87 empty] | 505 | [86 empty] | 505
[44 empty] | 506 | [87 empty] | 506 | [86 empty] | 506
[44 empty] | 507 | [87 empty] | 507 | [86 empty] | 507
[44 empty] | 508 | [87 empty] | 508 | [86 empty] | 508
[44 empty] | 509 | [87 empty] | 509 | [86 empty] | 509
[44 empty] | 510 | [87 empty] | 510 | [86 empty] | 510
[44 empty] | 511 | [87 empty] | 511 | [86 empty] | 511
[44 empty] | 512 | [87 empty] | 512 | [86 empty] | 512
[44 empty] | 513 | [87 empty] | 513 | [86 empty] | 513
[44 empty] | 514 | [87 empty] | 514 | [86 empty] | 514
[44 empty] | 515 | [87 empty] | 515 | [86 empty] | 515
[44 empty] | 516 | [87 empty] | 516 | [86 empty] | 516
[44 empty] | 517 | [87 empty] | 517 | [86 empty] | 517
[44 empty] | 518 | [87 empty] | 518 | [86 empty] | 518
[44 empty] | 519 | [87 empty] | 519 | [86 empty] | 519
[44 empty] | 520 | [87 empty] | 520 | [86 empty] | 520
[44 empty] | 521 | [87 empty] | 521 | [86 empty] | 521
[44 empty] | 522 | [87 empty] | 522 | [86 empty] | 522
[44 empty] | 523 | [87 empty] | 523 | [86 empty] | 523
[44 empty] | 524 | [87 empty] | 524 | [86 empty] | 524
[44 empty] | 525 | [87 empty] | 525 | [86 empty] | 525
[44 empty] | 526 | [87 empty] | 526 | [86 empty] | 526
[44 empty] | 527 | [87 empty] | 527 | [86 empty] | 527
[44 empty] | 528 | [87 empty] | 528 | [86 empty] | 528
[44 empty] | 529 | [87 empty] | 529 | [86 empty] | 529
[44 empty] | 530 | [87 empty] | 530 | [86 empty] | 530
[44 empty] | 531 | [87 empty] | 531 | [86 empty] | 531
[44 empty] | 532 | [87 empty] | 532 | [86 empty] | 532
[44 empty] | 533 | [87 empty] | 533 | [86 empty] | 533
[44 empty] | 534 | [87 empty] | 534 | [86 empty] | 534
[44 empty] | 535 | [87 empty] | 535 | [86 empty] | 535
[44 empty] | 536 | [87 empty] | 536 | [86 empty] | 536
[44 empty] | 537 | [87 empty] | 537 | [86 empty] | 537
[44 empty] | 538 | [87 empty] | 538 | [86 empty] | 538
[44 empty] | 539 | [87 empty] | 539 | [86 empty] | 539
[44 empty] | 540 | [87 empty] | 540 | [86 empty] | 540
[44 empty] | 541 | [87 empty] | 541 | [86 empty] | 541
[44 empty] | 542 | [87 empty] | 542 | [86 empty] | 542
[44 empty] | 543 | [87 empty] | 543 | [86 empty] | 543
[44 empty] | 544 | [87 empty] | 544 | [86 empty] | 544
[44 empty] | 545 | [87 empty] | 545 | [86 empty] | 545
[44 empty] | 546 | [87 empty] | 546 | [86 empty] | 546
[44 empty] | 547 | [87 empty] | 547 | [86 empty] | 547
[44 empty] | 548 | [87 empty] | 548 | [86 empty] | 548
[44 empty] | 549 | [87 empty] | 549 | [86 empty] | 549
[44 empty] | 550 | [87 empty] | 550 | [86 empty] | 550
[44 empty] | 551 | [87 empty] | 551 | [86 empty] | 551
[44 empty] | 552 | [87 empty] | 552 | [86 empty] | 552
[44 empty] | 553 | [87 empty] | 553 | [86 empty] | 553
[44 empty] | 554 | [87 empty] | 554 | [86 empty] | 554
[44 empty] | 555 | [87 empty] | 555 | [86 empty] | 555
[44 empty] | 556 | [87 empty] | 556 | [86 empty] | 556
[44 empty] | 557 | [87 empty] | 557 | [86 empty] | 557
[44 empty] | 558 | [87 empty] | 558 | [86 empty] | 558
[44 empty] | 559 | [87 empty] | 559 | [86 empty] | 559
[44 empty] | 560 | [87 empty] | 560 | [86 empty] | 560
[44 empty] | 561 | [87 empty] | 561 | [86 empty] | 561
[44 empty] | 562 | [87 empty] | 562 | [86 empty] | 562
[44 empty] | 563 | [87 empty] | 563 | [86 empty] | 563
[44 empty] | 564 | [87 empty] | 564 | [86 empty] | 564
[44 empty] | 565 | [87 empty] | 565 | [86 empty] | 565
[44 empty] | 566 | [87 empty] | 566 | [86 empty] | 566
[44 empty] | 567 | [87 empty] | 567 | [86 empty] | 567
[44 empty] | 568 | [87 empty] | 568 | [86 empty] | 568
[44 empty] | 569 | [87 empty] | 569 | [86 empty] | 569
[44 empty] | 570 | [87 empty] | 570 | [86 empty] | 570
[44 empty] | 571 | [87 empty] | 571 | [86 empty] | 571
[44 empty] | 572 | [87 empty] | 572 | [86 empty] | 572
[44 empty] | 573 | [87 empty] | 573 | [86 empty] | 573
[44 empty] | 574 | [87 empty] | 574 | [86 empty] | 574
[44 empty] | 575 | [87 empty] | 575 | [86 empty] | 575
[44 empty] | 576 | [87 empty] | 576 | [86 empty] | 576
[44 empty] | 577 | [87 empty] | 577 | [86 empty] | 577
[44 empty] | 578 | [87 empty] | 578 | [86 empty] | 578
[44 empty] | 579 | [87 empty] | 579 | [86 empty] | 579
[44 empty] | 580 | [87 empty] | 580 | [86 empty] | 580
[44 empty] | 581 | [87 empty] | 581 | [86 empty] | 581
[44 empty] | 582 | [87 empty] | 582 | [86 empty] | 582
[44 empty] | 583 | [87 empty] | 583 | [86 empty] | 583
[44 empty] | 584 | [87 empty] | 584 | [86 empty] | 584
[44 empty] | 585 | [87 empty] | 585 | [86 empty] | 585
[44 empty] | 586 | [87 empty] | 586 | [86 empty] | 586
[44 empty] | 587 | [87 empty] | 587 | [86 empty] | 587
[44 empty] | 588 | [87 empty] | 588 | [86 empty] | 588
[44 empty] | 589 | [87 empty] | 589 | [86 empty] | 589
[44 empty] | 590 | [87 empty] | 590 | [86 empty] | 590
[44 empty] | 591 | [87 empty] | 591 | [86 empty] | 591
[44 empty] | 592 | [87 empty] | 592 | [86 empty] | 592
[44 empty] | 593 | [87 empty] | 593 | [86 empty] | 593
[44 empty] | 594 | [87 empty] | 594 | [86 empty] | 594
[44 empty] | 595 | [87 empty] | 595 | [86 empty] | 595
[44 empty] | 596 | [87 empty] | 596 | [86 empty] | 596
[44 empty] | 597 | [87 empty] | 597 | [86 empty] | 597
[44 empty] | 598 | [87 empty] | 598 | [86 empty] | 598
[44 empty] | 599 | [87 empty] | 599 | [86 empty] | 599
[44 empty] | 600 | [87 empty] | 600 | [86 empty] | 600
[44 empty] | 601 | [87 empty] | 601 | [86 empty] | 601
[44 empty] | 602 | [87 empty] | 602 | [86 empty] | 602
[44 empty] | 603 | [87 empty] | 603 | [86 empty] | 603
[44 empty] | 604 | [87 empty] | 604 | [86 empty] | 604
[44 empty] | 605 | [87 empty] | 605 | [86 empty] | 605
[44 empty] | 606 | [87 empty] | 606 | [86 empty] | 606
[44 empty] | 607 | [87 empty] | 607 | [86 empty] | 607
[44 empty] | 608 | [87 empty] | 608 | [86 empty] | 608
[44 empty] | 609 | [87 empty] | 609 | [86 empty] | 609
[44 empty] | 610 | [87 empty] | 610 | [86 empty] | 610
[44 empty] | 611 | [87 empty] | 611 | [86 empty] | 611
[44 empty] | 612 | [87 empty] | 612 | [86 empty] | 612
[44 empty] | 613 | [87 empty] | 613 | [86 empty] | 613
[44 empty] | 614 | [87 empty] | 614 | [86 empty] | 614
[44 empty] | 615 | [87 empty] | 615 | [86 empty] | 615
[44 empty] | 616 | [87 empty] | 616 | [86 empty] | 616
[44 empty] | 617 | [87 empty] | 617 | [86 empty] | 617
[44 empty] | 618 | [87 empty] | 618 | [86 empty] | 618
[44 empty] | 619 | [87 empty] | 619 | [86 empty] | 619
[44 empty] | 620 | [87 empty] | 620 | [86 empty] | 620
[44 empty] | 621 | [87 empty] | 621 | [86 empty] | 621
[44 empty] | 622 | [87 empty] | 622 | [86 empty] | 622
[44 empty] | 623 | [87 empty] | 623 | [86 empty] | 623
[44 empty] | 624 | [87 empty] | 624 | [86 empty] | 624
[44 empty] | 625 | [87 empty] | 625 | [86 empty] | 625
[44 empty] | 626 | [87 empty] | 626 | [86 empty] | 626
[44 empty] | 627 | [87 empty] | 627 | [86 empty] | 627
[44 empty] | 628 | [87 empty] | 628 | [86 empty] | 628
[44 empty] | 629 | [87 empty] | 629 | [86 empty] | 629
[44 empty] | 630 | [87 empty] | 630 | [86 empty] | 630
[44 empty] | 631 | [87 empty] | 631 | [86 empty] | 631
[44 empty] | 632 | [87 empty] | 632 | [86 empty] | 632
[44 empty] | 633 | [87 empty] | 633 | [86 empty] | 633
[44 empty] | 634 | [87 empty] | 634 | [86 empty] | 634
[44 empty] | 635 | [87 empty] | 635 | [86 empty] | 635
[44 empty] | 636 | [87 empty] | 636 | [86 empty] | 636
[44 empty] | 637 | [87 empty] | 637 | [86 empty] | 637
[44 empty] | 638 | [87 empty] | 638 | [86 empty] | 638
[44 empty] | 639 | [87 empty] | 639 | [86 empty] | 639
[44 empty] | 640 | [87 empty] | 640 | [86 empty] | 640
[44 empty] | 641 | [87 empty] | 641 | [86 empty] | 641
[44 empty] | 642 | [87 empty] | 642 | [86 empty] | 642
[44 empty] | 643 | [87 empty] | 643 | [86 empty] | 643
[44 empty] | 644 | [87 empty] | 644 | [86 empty] | 644
[44 empty] | 645 | [87 empty] | 645 | [86 empty] | 645
[44 empty] | 646 | [87 empty] | 646 | [86 empty] | 646
[44 empty] | 647 | [87 empty] | 647 | [86 empty] | 647
[44 empty] | 648 | [87 empty] | 648 | [86 empty] | 648
[44 empty] | 649 | [87 empty] | 649 | [86 empty] | 649
[44 empty] | 650 | [87 empty] | 650 | [86 empty] | 650
[44 empty] | 651 | [87 empty] | 651 | [86 empty] | 651
[44 empty] | 652 | [87 empty] | 652 | [86 empty] | 652
[44 empty] | 653 | [87 empty] | 653 | [86 empty] | 653
[44 empty] | 654 | [87 empty] | 654 | [86 empty] | 654
[44 empty] | 655 | [87 empty] | 655 | [86 empty] | 655
[44 empty] | 656 | [87 empty] | 656 | [86 empty] | 656
[44 empty] | 657 | [87 empty] | 657 | [86 empty] | 657
[44 empty] | 658 | [87 empty] | 658 | [86 empty] | 658
[44 empty] | 659 | [87 empty] | 659 | [86 empty] | 659
[44 empty] | 660 | [87 empty] | 660 | [86 empty] | 660
[44 empty] | 661 | [87 empty] | 661 | [86 empty] | 661
[44 empty] | 662 | [87 empty] | 662 | [86 empty] | 662
[44 empty] | 663 | [87 empty] | 663 | [86 empty] | 663
[44 empty] | 664 | [87 empty] | 664 | [86 empty] | 664
[44 empty] | 665 | [87 empty] | 665 | [86 empty] | 665
[44 empty] | 666 | [87 empty] | 666 | [86 empty] | 666
[44 empty] | 667 | [87 empty] | 667 | [86 empty] | 667
[44 empty] | 668 | [87 empty] | 668 | [86 empty] | 668
[44 empty] | 669 | [87 empty] | 669 | [86 empty] | 669
[44 empty] | 670 | [87 empty] | 670 | [86 empty] | 670
[44 empty] | 671 | [87 empty] | 671 | [86 empty] | 671
[44 empty] | 672 | [87 empty] | 672 | [86 empty] | 672
[44 empty] | 673 | [87 empty] | 673 | [86 empty] | 673
[44 empty] | 674 | [87 empty] | 674 | [86 empty] | 674
[44 empty] | 675 | [87 empty] | 675 | [86 empty] | 675
[44 empty] | 676 | [87 empty] | 676 | [86 empty] | 676
[44 empty] | 677 | [87 empty] | 677 | [86 empty] | 677
[44 empty] | 678 | [87 empty] | 678 | [86 empty] | 678
[44 empty] | 679 | [87 empty] | 679 | [86 empty] | 679
[44 empty] | 680 | [87 empty] | 680 | [86 empty] | 680
[44 empty] | 681 | [87 empty] | 681 | [86 empty] | 681
[44 empty] | 682 | [87 empty] | 682 | [86 empty] | 682
[44 empty] | 683 | [87 empty] | 683 | [86 empty] | 683
[44 empty] | 684 | [87 empty] | 684 | [86 empty] | 684
[44 empty] | 685 | [87 empty] | 685 | [86 empty] | 685
[44 empty] | 686 | [87 empty] | 686 | [86 empty] | 686
[44 empty] | 687 | [87 empty] | 687 | [86 empty] | 687
[44 empty] | 688 | [87 empty] | 688 | [86 empty] | 688
[44 empty] | 689 | [87 empty] | 689 | [86 empty] | 689
[44 empty] | 690 | [87 empty] | 690 | [86 empty] | 690
[44 empty] | 691 | [87 empty] | 691 | [86 empty] | 691
[44 empty] | 692 | [87 empty] | 692 | [86 empty] | 692
[44 empty] | 693 | [87 empty] | 693 | [86 empty] | 693
[44 empty] | 694 | [87 empty] | 694 | [86 empty] | 694
[44 empty] | 695 | [87 empty] | 695 | [86 empty] | 695
[44 empty] | 696 | [87 empty] | 696 | [86 empty] | 696
[44 empty] | 697 | [87 empty] | 697 | [86 empty] | 697
[44 empty] | 698 | [87 empty] | 698 | [86 empty] | 698
[44 empty] | 699 | [87 empty] | 699 | [86 empty] | 699
[44 empty] | 700 | [87 empty] | 700 | [86 empty] | 700
[44 empty] | 701 | [87 empty] | 701 | [86 empty] | 701
[44 empty] | 702 | [87 empty] | 702 | [86 empty] | 702
[44 empty] | 703 | [87 empty] | 703 | [86 empty] | 703
[44 empty] | 704 | [87 empty] | 704 | [86 empty] | 704
[44 empty] | 705 | [87 empty] | 705 | [86 empty] | 705
[44 empty] | 706 | [87 empty] | 706 | [86 empty] | 706
[44 empty] | 707 | [87 empty] | 707 | [86 empty] | 707
[44 empty] | 708 | [87 empty] | 708 | [86 empty] | 708
[44 empty] | 709 | [87 empty] | 709 | [86 empty] | 709
[44 empty] | 710 | [87 empty] | 710 | [86 empty] | 710
[44 empty] | 711 | [87 empty] | 711 | [86 empty] | 711
[44 empty] | 712 | [87 empty] | 712 | [86 empty] | 712
[44 empty] | 713 | [87 empty] | 713 | [86 empty] | 713
[44 empty] | 714 | [87 empty] | 714 | [86 empty] | 714
[44 empty] | 715 | [87 empty] | 715 | [86 empty] | 715
[44 empty] | 716 | [87 empty] | 716 | [86 empty] | 716
[44 empty] | 717 | [87 empty] | 717 | [86 empty] | 717
[44 empty] | 718 | [87 empty] | 718 | [86 empty] | 718
[44 empty] | 719 | [87 empty] | 719 | [86 empty] | 719
[44 empty] | 720 | [87 empty] | 720 | [86 empty] | 720
[44 empty] | 721 | [87 empty] | 721 | [86 empty] | 721
[44 empty] | 722 | [87 empty] | 722 | [86 empty] | 722
[44 empty] | 723 | [87 empty] | 723 | [86 empty] | 723
[44 empty] | 724 | [87 empty] | 724 | [86 empty] | 724
[44 empty] | 725 | [87 empty] | 725 | [86 empty] | 725
[44 empty] | 726 | [87 empty] | 726 | [86 empty] | 726
[44 empty] | 727 | [87 empty] | 727 | [86 empty] | 727
[44 empty] | 728 | [87 empty] | 728 | [86 empty] | 728
[44 empty] | 729 | [87 empty] | 729 | [86 empty] | 729
[44 empty] | 730 | [87 empty] | 730 | [86 empty] | 730
[44 empty] | 731 | [87 empty] | 731 | [86 empty] | 731
[44 empty] | 732 | [87 empty] | 732 | [86 empty] | 732
[44 empty] | 733 | [87 empty] | 733 | [86 empty] | 733
[44 empty] | 734 | [87 empty] | 734 | [86 empty] | 734
[44 empty] | 735 | [87 empty] | 735 | [86 empty] | 735
[44 empty] | 736 | [87 empty] | 736 | [86 empty] | 736
[44 empty] | 737 | [87 empty] | 737 | [86 empty] | 737
[44 empty] | 738 | [87 empty] | 738 | [86 empty] | 738
[44 empty] | 739 | [87 empty] | 739 | [86 empty] | 739
[44 empty] | 740 | [87 empty] | 740 | [86 empty] | 740
[44 empty] | 741 | [87 empty] | 741 | [86 empty] | 741
[44 empty] | 742 | [87 empty] | 742 | [86 empty] | 742
[44 empty] | 743 | [87 empty] | 743 | [86 empty] | 743
[44 empty] | 744 | [87 empty] | 744 | [86 empty] | 744
[44 empty] | 745 | [87 empty] | 745 | [86 empty] | 745
[44 empty] | 746 | [87 empty] | 746 | [86 empty] | 746
[44 empty] | 747 | [87 empty] | 747 | [86 empty] | 747
[44 empty] | 748 | [87 empty] | 748 | [86 empty] | 748
[44 empty] | 749 | [87 empty] | 749 | [86 empty] | 749
[44 empty] | 750 | [87 empty] | 750 | [86 empty] | 750
[44 empty] | 751 | [87 empty] | 751 | [86 empty] | 751
[44 empty] | 752 | [87 empty] | 752 | [86 empty] | 752
[44 empty] | 753 | [87 empty] | 753 | [86 empty] | 753
[44 empty] | 754 | [87 empty] | 754 | [86 empty] | 754
[44 empty] | 755 | [87 empty] | 755 | [86 empty] | 755
[44 empty] | 756 | [87 empty] | 756 | [86 empty] | 756
[44 empty] | 757 | [87 empty] | 757 | [86 empty] | 757
[44 empty] | 758 | [87 empty] | 758 | [86 empty] | 758
[44 empty] | 759 | [87 empty] | 759 | [86 empty] | 759
[44 empty] | 760 | [87 empty] | 760 | [86 empty] | 760
[44 empty] | 761 | [87 empty] | 761 | [86 empty] | 761
[44 empty] | 762 | [87 empty] | 762 | [86 empty] | 762
[44 empty] | 763 | [87 empty] | 763 | [86 empty] | 763
[44 empty] | 764 | [87 empty] | 764 | [86 empty] | 764
[44 empty] | 765 | [87 empty] | 765 | [86 empty] | 765
[44 empty] | 766 | [87 empty] | 766 | [86 empty] | 766
[44 empty] | 767 | [87 empty] | 767 | [86 empty] | 767
[44 empty] | 768 | [87 empty] | 768 | [86 empty] | 768
[44 empty] | 769 | [87 empty] | 769 | [86 empty] | 769
[44 empty] | 770 | [87 empty] | 770 | [86 empty] | 770
[44 empty] | 771 | [87 empty] | 771 | [86 empty] | 771
[44 empty] | 772 | [87 empty] | 772 | [86 empty] | 772
[44 empty] | 773 | [87 empty] | 773 | [86 empty] | 773
[44 empty] | 774 | [87 empty] | 774 | [86 empty] | 774
[44 empty] | 775 | [87 empty] | 775 | [86 empty] | 775
[44 empty] | 776 | [87 empty] | 776 | [86 empty] | 776
[44 empty] | 777 | [87 empty] | 777 | [86 empty] | 777
[44 empty] | 778 | [87 empty] | 778 | [86 empty] | 778
[44 empty] | 779 | [87 empty] | 779 | [86 empty] | 779
[44 empty] | 780 | [87 empty] | 780 | [86 empty] | 780
[44 empty] | 781 | [87 empty] | 781 | [86 empty] | 781
[44 empty] | 782 | [87 empty] | 782 | [86 empty] | 782
[44 empty] | 783 | [87 empty] | 783 | [86 empty] | 783
[44 empty] | 784 | [87 empty] | 784 | [86 empty] | 784
[44 empty] | 785 | [87 empty] | 785 | [86 empty] | 785
[44 empty] | 786 | [87 empty] | 786 | [86 empty] | 786
[44 empty] | 787 | [87 empty] | 787 | [86 empty] | 787
[44 empty] | 788 | [87 empty] | 788 | [86 empty] | 788
[44 empty] | 789 | [87 empty] | 789 | [86 empty] | 789
[44 empty] | 790 | [87 empty] | 790 | [86 empty] | 790
[44 empty] | 791 | [87 empty] | 791 | [86 empty] | 791
[44 empty] | 792 | [87 empty] | 792 | [86 empty] | 792
[44 empty] | 793 | [87 empty] | 793 | [86 empty] | 793
[44 empty] | 794 | [87 empty] | 794 | [86 empty] | 794
[44 empty] | 795 | [87 empty] | 795 | [86 empty] | 795
[44 empty] | 796 | [87 empty] | 796 | [86 empty] | 796
[44 empty] | 797 | [87 empty] | 797 | [86 empty] | 797
[44 empty] | 798 | [87 empty] | 798 | [86 empty] | 798
[44 empty] | 799 | [87 empty] | 799 | [86 empty] | 799
[44 empty] | 800 | [87 empty] | 800 | [86 empty] | 800
[44 empty] | 801 | [87 empty] | 801 | [86 empty] | 801
[44 empty] | 802 | [87 empty] | 802 | [86 empty] | 802
[44 empty] | 803 | [87 empty] | 803 | [86 empty] | 803
[44 empty] | 804 | [87 empty] | 804 | [86 empty] | 804
[44 empty] | 805 | [87 empty] | 805 | [86 empty] | 805
[44 empty] | 806 | [87 empty] | 806 | [86 empty] | 806
[44 empty] | 807 | [87 empty] | 807 | [86 empty] | 807
[44 empty] | 808 | [87 empty] | 808 | [86 empty] | 808
[44 empty] | 809 | [87 empty] | 809 | [86 empty] | 809
[44 empty] | 810 | [87 empty] | 810 | [86 empty] | 810
[44 empty] | 811 | [87 empty] | 811 | [86 empty] | 811
[44 empty] | 812 | [87 empty] | 812 | [86 empty] | 812
[44 empty] | 813 | [87 empty] | 813 | [86 empty] | 813
[44 empty] | 814 | [87 empty] | 814 | [86 empty] | 814
[44 empty] | 815 | [87 empty] | 815 | [86 empty] | 815
[44 empty] | 816 | [87 empty] | 816 | [86 empty] | 816
[44 empty] | 817 | [87 empty] | 817 | [86 empty] | 817
[44 empty] | 818 | [87 empty] | 818 | [86 empty] | 818
[44 empty] | 819 | [87 empty] | 819 | [86 empty] | 819
[44 empty] | 820 | [87 empty] | 820 | [86 empty] | 820
[44 empty] | 821 | [87 empty] | 821 | [86 empty] | 821
[44 empty] | 822 | [87 empty] | 822 | [86 empty] | 822
[44 empty] | 823 | [87 empty] | 823 | [86 empty] | 823
[44 empty] | 824 | [87 empty] | 824 | [86 empty] | 824
[44 empty] | 825 | [87 empty] | 825 | [86 empty] | 825
[44 empty] | 826 | [87 empty] | 826 | [86 empty] | 826
[44 empty] | 827 | [87 empty] | 827 | [86 empty] | 827
[44 empty] | 828 | [87 empty] | 828 | [86 empty] | 828
[44 empty] | 829 | [87 empty] | 829 | [86 empty] | 829
[44 empty] | 830 | [87 empty] | 830 | [86 empty] | 830
[44 empty] | 831 | [87 empty] | 831 | [86 empty] | 831
[44 empty] | 832 | [87 empty] | 832 | [86 empty] | 832
[44 empty] | 833 | [87 empty] | 833 | [86 empty] | 833
[44 empty] | 834 | [87 empty] | 834 | [86 empty] | 834
[44 empty] | 835 | [87 empty] | 835 | [86 empty] | 835
[44 empty] | 836 | [87 empty] | 836 | [86 empty] | 836
[44 empty] | 837 | [87 empty] | 837 | [86 empty] | 837
[44 empty] | 838 | [87 empty] | 838 | [86 empty] | 838
[44 empty] | 839 | [87 empty] | 839 | [86 empty] | 839
[44 empty] | 840 | [87 empty] | 840 | [86 empty] | 840
[44 empty] | 841 | [87 empty] | 841 | [86 empty] | 841
[44 empty] | 842 | [87 empty] | 842 | [86 empty] | 842
[44 empty] | 843 | [87 empty] | 843 | [86 empty] | 843
[44 empty] | 844 | [87 empty] | 844 | [86 empty] | 844
[44 empty] | 845 | [87 empty] | 845 | [86 empty] | 845
[44 empty] | 846 | [87 empty] | 846 | [86 empty] | 846
[44 empty] | 847 | [87 empty] | 847 | [86 empty] | 847
[44 empty] | 848 | [87 empty] | 848 | [86 empty] | 848
[44 empty] | 849 | [87 empty] | 849 | [86 empty] | 849
[44 empty] | 850 | [87 empty] | 850 | [86 empty] | 850
[44 empty] | 851 | [87 empty] | 851 | [86 empty] | 851
[44 empty] | 852 | [87 empty] | 852 | [86 empty] | 852
[44 empty] | 853 | [87 empty] | 853 | [86 empty] | 853
[44 empty] | 854 | [87 empty] | 854 | [86 empty] | 854
[44 empty] | 855 | [87 empty] | 855 | [86 empty] | 855
[44 empty] | 856 | [87 empty] | 856 | [86 empty] | 856
[44 empty] | 857 | [87 empty] | 857 | [86 empty] | 857
[44 empty] | 858 | [87 empty] | 858 | [86 empty] | 858
[44 empty] | 859 | [87 empty] | 859 | [86 empty] | 859
[44 empty] | 860 | [87 empty] | 860 | [86 empty] | 860
[44 empty] | 861 | [87 empty] | 861 | [86 empty] | 861
[44 empty] | 862 | [87 empty] | 862 | [86 empty] | 862
[44 empty] | 863 | [87 empty] | 863 | [86 empty] | 863
[44 empty] | 864 | [87 empty] | 864 | [86 empty] | 864
[44 empty] | 865 | [87 empty] | 865 | [86 empty] | 865
[44 empty] | 866 | [87 empty] | 866 | [86 empty] | 866
[44 empty] | 867 | [87 empty] | 867 | [86 empty] | 867
[44 empty] | 868 | [87 empty] | 868 | [86 empty] | 868
[44 empty] | 869 | [87 empty] | 869 | [86 empty] | 869
[44 empty] | 870 | [87 empty] | 870 | [86 empty] | 870
[44 empty] | 871 | [87 empty] | 871 | [86 empty] | 871
[44 empty] | 872 | [87 empty] | 872 | [86 empty] | 872
[44 empty] | 873 | [87 empty] | 873 | [86 empty] | 873
[44 empty] | 874 | [87 empty] | 874 | [86 empty] | 874
[44 empty] | 875 | [87 empty] | 875 | [86 empty] | 875
[44 empty] | 876 | [87 empty] | 876 | [86 empty] | 876
[44 empty] | 877 | [87 empty] | 877 | [86 empty] | 877
[44 empty] | 878 | [87 empty] | 878 | [86 empty] | 878
[44 empty] | 879 | [87 empty] | 879 | [86 empty] | 879
[44 empty] | 880 | [87 empty] | 880 | [86 empty] | 880
[44 empty] | 881 | [87 empty] | 881 | [86 empty] | 881
[44 empty] | 882 | [87 empty] | 882 | [86 empty] | 882
[44 empty] | 883 | [87 empty] | 883 | [86 empty] | 883
[44 empty] | 884 | [87 empty] | 884 | [86 empty] | 884
[44 empty] | 885 | [87 empty] | 885 | [86 empty] | 885
[44 empty] | 886 | [87 empty] | 886 | [86 empty] | 886
[44 empty] | 887 | [87 empty] | 887 | [86 empty] | 887
[44 empty] | 888 | [87 empty] | 888 | [86 empty] | 888
[44 empty] | 889 | [87 empty] | 889 | [86 empty] | 889
[44 empty] | 890 | [87 empty] | 890 | [86 empty] | 890
[44 empty] | 891 | [87 empty] | 891 | [86 empty] | 891
[44 empty] | 892 | [87 empty] | 892 | [86 empty] | 892
[44 empty] | 893 | [87 empty] | 893 | [86 empty] | 893
[44 empty] | 894 | [87 empty] | 894 | [86 empty] | 894
[44 empty] | 895 | [87 empty] | 895 | [86 empty] | 895
[44 empty] | 896 | [87 empty] | 896 | [86 empty] | 896
[44 empty] | 897 | [87 empty] | 897 | [86 empty] | 897
[44 empty] | 898 | [87 empty] | 898 | [86 empty] | 898
[44 empty] | 899 | [87 empty] | 899 | [86 empty] | 899
[44 empty] | 900 | [87 empty] | 900 | [86 empty] | 900
[44 empty] | 901 | [87 empty] | 901 | [86 empty] | 901
[44 empty] | 902 | [87 empty] | 902 | [86 empty] | 902
[44 empty] | 903 | [87 empty] | 903 | [86 empty] | 903
[44 empty] | 904 | [87 empty] | 904 | [86 empty] | 904
[44 empty] | 905 | [87 empty] | 905 | [86 empty] | 905
[44 empty] | 906 | [87 empty] | 906 | [86 empty] | 906
[44 empty] | 907 | [87 empty] | 907 | [86 empty] | 907
[44 empty] | 908 | [87 empty] | 908 | [86 empty] | 908
[44 empty] | 909 | [87 empty] | 909 | [86 empty] | 909
[44 empty] | 910 | [87 empty] | 910 | [86 empty] | 910
[44 empty] | 911 | [87 empty] | 911 | [86 empty] | 911
[44 empty] | 912 | [87 empty] | 912 | [86 empty] | 912
[44 empty] | 913 | [87 empty] | 913 | [86 empty] | 913
[44 empty] | 914 | [87 empty] | 914 | [86 empty] | 914
[44 empty] | 915 | [87 empty] | 915 | [86 empty] | 915
[44 empty] | 916 | [87 empty] | 916 | [86 empty] | 916
[44 empty] | 917 | [87 empty] | 917 | [86 empty] | 917
[44 empty] | 918 | [87 empty] | 918 | [86 empty] | 918
[44 empty] | 919 | [87 empty] | 919 | [86 empty] | 919
[44 empty] | 920 | [87 empty] | 920 | [86 empty] | 920
[44 empty] | 921 | [87 empty] | 921 | [86 empty] | 921
[44 empty] | 922 | [87 empty] | 922 | [86 empty] | 922
[44 empty] | 923 | [87 empty] | 923 | [86 empty] | 923
[44 empty] | 924 | [87 empty] | 924 | [86 empty] | 924
[44 empty] | 925 | [87 empty] | 925 | [86 empty] | 925
[44 empty] | 926 | [87 empty] | 926 | [86 empty] | 926
[44 empty] | 927 | [87 empty] | 927 | [86 empty] | 927
[44 empty] | 928 | [87 empty] | 928 | [86 empty] | 928
[44 empty] | 929 | [87 empty] | 929 | [86 empty] | 929
[44 empty] | 930 | [87 empty] | 930 | [86 empty] | 930
[44 empty] | 931 | [87 empty] | 931 | [86 empty] | 931
[44 empty] | 932 | [87 empty] | 932 | [86 empty] | 932
[44 empty] | 933 | [87 empty] | 933 | [86 empty] | 933
[44 empty] | 934 | [87 empty] | 934 | [86 empty] | 934
[44 empty] | 935 | [87 empty] | 935 | [86 empty] | 935
[44 empty] | 936 | [87 empty] | 936 | [86 empty] | 936
[44 empty] | 937 | [87 empty] | 937 | [86 empty] | 937
[44 empty] | 938 | [87 empty] | 938 | [86 empty] | 938
[44 empty] | 939 | [87 empty] | 939 | [86 empty] | 939
[44 empty] | 940 | [87 empty] | 940 | [86 empty] | 940
[44 empty] | 941 | [87 empty] | 941 | [86 empty] | 941
[44 empty] | 942 | [87 empty] | 942 | [86 empty] | 942
[44 empty] | 943 | [87 empty] | 943 | [86 empty] | 943
[44 empty] | 944 | [87 empty] | 944 | [86 empty] | 944
[44 empty] | 945 | [87 empty] | 945 | [86 empty] | 945
[44 empty] | 946 | [87 empty] | 946 | [86 empty] | 946
[44 empty] | 947 | [87 empty] | 947 | [86 empty] | 947
[44 empty] | 948 | [87 empty] | 948 | [86 empty] | 948
[44 empty] | 949 | [87 empty] | 949 | [86 empty] | 949
[44 empty] | 950 | [87 empty] | 950 | [86 empty] | 950
[44 empty] | 951 | [87 empty] | 951 | [86 empty] | 951
[44 empty] | 952 | [87 empty] | 952 | [86 empty] | 952
[44 empty] | 953 | [87 empty] | 953 | [86 empty] | 953
[44 empty] | 954 | [87 empty] | 954 | [86 empty] | 954
[44 empty] | 955 | [87 empty] | 955 | [86 empty] | 955
[44 empty] | 956 | [87 empty] | 956 | [86 empty] | 956
[44 empty] | 957 | [87 empty] | 957 | [86 empty] | 957
[44 empty] | 958 | [87 empty] | 958 | [86 empty] | 958
[44 empty] | 959 | [87 empty] | 959 | [86 empty] | 959
[44 empty] | 960 | [87 empty] | 960 | [86 empty] | 960
[44 empty] | 961 | [87 empty] | 961 | [86 empty] | 961
[44 empty] | 962 | [87 empty] | 962 | [86 empty] | 962
[44 empty] | 963 | [87 empty] | 963 | [86 empty] | 963
[44 empty] | 964 | [87 empty] | 964 | [86 empty] | 964
[44 empty] | 965 | [87 empty] | 965 | [86 empty] | 965
[44 empty] | 966 | [87 empty] | 966 | [86 empty] | 966
[44 empty] | 967 | [87 empty] | 967 | [86 empty] | 967
[44 empty] | 968 | [87 empty] | 968 | [86 empty] | 968
[44 empty] | 969 | [87 empty] | 969 | [86 empty] | 969
[44 empty] | 970 | [87 empty] | 970 | [86 empty] | 970
[44 empty] | 971 | [87 empty] | 971 | [86 empty] | 971
[44 empty] | 972 | [87 empty] | 972 | [86 empty] | 972
[44 empty] | 973 | [87 empty] | 973 | [86 empty] | 973
[44 empty] | 974 | [87 empty] | 974 | [86 empty] | 974
[44 empty] | 975 | [87 empty] | 975 | [86 empty] | 975
[44 empty] | 976 | [87 empty] | 976 | [86 empty] | 976
[44 empty] | 977 | [87 empty] | 977 | [86 empty] | 977
[44 empty] | 978 | [87 empty] | 978 | [86 empty] | 978
[44 empty] | 979 | [87 empty] | 979 | [86 empty] | 979
[44 empty] | 980 | [87 empty] | 980 | [86 empty] | 980
[44 empty] | 981 | [87 empty] | 981 | [86 empty] | 981
[44 empty] | 982 | [87 empty] | 982 | [86 empty] | 982
[44 empty] | 983 | [87 empty] | 983 | [86 empty] | 983
[44 empty] | 984 | [87 empty] | 984 | [86 empty] | 984
[44 empty] | 985 | [87 empty] | 985 | [86 empty] | 985
[44 empty] | 986 | [87 empty] | 986 | [86 empty] | 986
[44 empty] | 987 | [87 empty] | 987 | [86 empty] | 987
[44 empty] | 988 | [87 empty] | 988 | [86 empty] | 988
[44 empty] | 989 | [87 empty] | 989 | [86 empty] | 989
[44 empty] | 990 | [87 empty] | 990 | [86 empty] | 990
[44 empty] | 991 | [87 empty] | 991 | [86 empty] | 991
[44 empty] | 992 | [87 empty] | 992 | [86 empty] | 992
[44 empty] | 993 | [87 empty] | 993 | [86 empty] | 993
[44 empty] | 994 | [87 empty] | 994 | [86 empty] | 994
[44 empty] | 995 | [87 empty] | 995 | [86 empty] | 995
[44 empty] | 996 | [87 empty] | 996 | [86 empty] | 996
[44 empty] | 997 | [87 empty] | 997 | [86 empty] | 997
[44 empty] | 998 | [87 empty] | 998 | [86 empty] | 998
[44 empty] | 999 | [87 empty] | 999 | [86 empty] | 999
[44 empty] | 1000 | [87 empty] | 1000 | [86 empty] | 1000
[44 empty] | 1001 | [87 empty] | 1001 | [86 empty] | 1001
[44 empty] | 1002 | [87 empty] | 1002 | [86 empty] | 1002
[44 empty] | 1003 | [87 empty] | 1003 | [86 empty] | 1003
[44 empty] | 1004 | [87 empty] | 1004 | [86 empty] | 1004
[44 empty] | 1005 | [87 empty] | 1005 | [86 empty] | 1005
[44 empty] | 1006 | [87 empty] | 1006 | [86 empty] | 1006
[44 empty] | 1007 | [87 empty] | 1007 | [86 empty] | 1007
[44 empty] | 1008 | [87 empty] | 1008 | [86 empty] | 1008
[44 empty] | 1009 | [87 empty] | 1009 | [86 empty] | 1009
[44 empty] | 1010 | [87 empty] | 1010 | [86 empty] | 1010
[44 empty] | 1011 | [87 empty] | 1011 | [86 empty] | 1011
[44 empty] | 1012 | [87 empty] | 1012 | [86 empty] | 1012
[44 empty] | 1013 | [87 empty] | 1013 | [86 empty] | 1013
[44 empty] | 1014 | [87 empty] | 1014 | [86 empty] | 1014
[44 empty] | 1015 | [87 empty] | 1015 | [86 empty] | 1015
[44 empty] | 1016 | [87 empty] | 1016 | [86 empty] | 1016
[44 empty] | 1017 | [87 empty] | 1017 | [86 empty] | 1017
[44 empty] | 1018 | [87 empty] | 1018 | [86 empty] | 1018
[44 empty] | 1019 | [87 empty] | 1019 | [86 empty] | 1019
[44 empty] | 1020 | [87 empty] | 1020 | [86 empty] | 1020
[44 empty] | 1021 | [87 empty] | 1021 | [86 empty] | 1021
[44 empty] | 1022 | [87 empty] | 1022 | [86 empty] | 1022
[44 empty] | 1023 | [87 empty] | 1023 | [86 empty] | 1023
[44 empty] | 1024 | [87 empty] | 1024 | [86 empty] | 1024
[44 empty] | 1025 | [87 empty] | 1025 | [86 empty] | 1025
[44 empty] | 1026 | [87 empty] | 1026 | [86 empty] | 1026
[44 empty] | 1027 | [87 empty] | 1027 | [86 empty] | 1027
[44 empty] | 1028 | [87 empty] | 1028 | [86 empty] | 1028
[44 empty] | 1029 | [87 empty] | 1029 | [86 empty] | 1029
[44 empty] | 1030 | [87 empty] | 1030 | [86 empty] | 1030
[44 empty] | 1031 | [87 empty] | 1031 | [86 empty] | 1031
[44 empty] | 1032 | [87 empty] | 1032 | [86 empty] | 1032
[44 empty] | 1033 | [87 empty] | 1033 | [86 empty] | 1033
[44 empty] | 1034 | [87 empty] | 1034 | [86 empty] | 1034
[44 empty] | 1035 | [87 empty] | 1035 | [86 empty] | 1035
[44 empty] | 1036 | [87 empty] | 1036 | [86 empty] | 1036
[44 empty] | 1037 | [87 empty] | 1037 | [86 empty] | 1037
[44 empty] | 1038 | [87 empty] | 1038 | [86 empty] | 1038
[44 empty] | 1039 | [87 empty] | 1039 | [86 empty] | 1039
[44 empty] | 1040 | [87 empty] | 1040 | [86 empty] | 1040
[44 empty] | 1041 | [87 empty] | 1041 | [86 empty] | 1041
[44 empty] | 1042 | [87 empty] | 1042 | [86 empty] | 1042
[44 empty] | 1043 | [87 empty] | 1043 | [86 empty] | 1043
[44 empty] | 1044 | [87 empty] | 1044 | [86 empty] | 1044
[44 empty] | 1045 | [87 empty] | 1045 | [86 empty] | 1045
[44 empty] | 1046 | [87 empty] | 1046 | [86 empty] | 1046
[44 empty] | 1047 | [87 empty] | 1047 | [86 empty] | 1047
[44 empty] | 1048 | [87 empty] | 1048 | [86 empty] | 1048
[44 empty] | 1049 | [87 empty] | 1049 | [86 empty] | 1049
[44 empty] | 1050 | [87 empty] | 1050 | [86 empty] | 1050
[44 empty] | 1051 | [87 empty] | 1051 | [86 empty] | 1051
[44 empty] | 1052 | [87 empty] | 1052 | [86 empty] | 1052
[44 empty] | 1053 | [87 empty] | 1053 | [86 empty] | 1053
[44 empty] | 1054 | [87 empty] | 1054 | [86 empty] | 1054
[44 empty] | 1055 | [87 empty] | 1055 | [86 empty] | 1055
[44 empty] | 1056 | [87 empty] | 1056 | [86 empty] | 1056
[44 empty] | 1057 | [87 empty] | 1057 | [86 empty] | 1057
[44 empty] | 1058 | [87 empty] | 1058 | [86 empty] | 1058
[44 empty] | 1059 | [87 empty] | 1059 | [86 empty] | 1059
[44 empty] | 1060 | [87 empty] | 1060 | [86 empty] | 1060
[44 empty] | 1061 | [87 empty] | 1061 | [86 empty] | 1061
[44 empty] | 1062 | [87 empty] | 1062 | [86 empty] | 1062
[44 empty] | 1063 | [87 empty] | 1063 | [86 empty] | 1063
[44 empty] | 1064 | [87 empty] | 1064 | [86 empty] | 1064
[44 empty] | 1065 | [87 empty] | 1065 | [86 empty] | 1065
[44 empty] | 1066 | [87 empty] | 1066 | [86 empty] | 1066
[44 empty] | 1067 | [87 empty] | 1067 | [86 empty] | 1067
[44 empty] | 1068 | [87 empty] | 1068 | [86 empty] | 1068
[44 empty] | 1069 | [87 empty] | 1069 | [86 empty] | 1069
[44 empty] | 1070 | [87 empty] | 1070 | [86 empty] | 1070
[44 empty] | 1071 | [87 empty] | 1071 | [86 empty] | 1071
[44 empty] | 1072 | [87 empty] | 1072 | [86 empty] | 1072
[44 empty] | 1073 | [87 empty] | 1073 | [86 empty] | 1073
[44 empty] | 1074 | [87 empty] | 1074 | [86 empty] | 1074
[44 empty] | 1075 | [87 empty] | 1075 | [86 empty] | 1075
[44 empty] | 1076 | [87 empty] | 1076 | [86 empty] | 1076
[44 empty] | 1077 | [87 empty] | 1077 | [86 empty] | 1077
[44 empty] | 1078 | [87 empty] | 1078 | [86 empty] | 1078
[44 empty] | 1079 | [87 empty] | 1079 | [86 empty] | 1079
[44 empty] | 1080 | [87 empty] | 1080 | [86 empty] | 1080
[44 empty] | 1081 | [87 empty] | 1081 | [86 empty] | 1081
[44 empty] | 1082 | [87 empty] | 1082 | [86 empty] | 1082
[44 empty] | 1083 | [87 empty] | 1083 | [86 empty] | 1083
[44 empty] | 1084 | [87 empty] | 1084 | [86 empty] | 1084
[44 empty] | 1085 | [87 empty] | 1085 | [86 empty] | 1085
[44 empty] | 1086 | [87 empty] | 1086 | [86 empty] | 1086
[44 empty] | 1087 | [87 empty] | 1087 | [86 empty] | 1087
[44 empty] | 1088 | [87 empty] | 1088 | [86 empty] | 1088
[44 empty] | 1089 | [87 empty] | 1089 | [86 empty] | 1089
[44 empty] | 1090 | [87 empty] | 1090 | [86 empty] | 1090
[44 empty] | 1091 | [87 empty] | 1091 | [86 empty] | 1091
[44 empty] | 1092 | [87 empty] | 1092 | [86 empty] | 1092
[44 empty] | 1093 | [87 empty] | 1093 | [86 empty] | 1093
[44 empty] | 1094 | [87 empty] | 1094 | [86 empty] | 1094
[44 empty] | 1095 | [87 empty] | 1095 | [86 empty] | 1095
[44 empty] | 1096 | [87 empty] | 1096 | [86 empty] | 1096
[44 empty] | 1097 | [87 empty] | 1097 | [86 empty] | 1097
[44 empty] | 1098 | [87 empty] | 1098 | [86 empty] | 1098
[44 empty] | 1099 | [87 empty] | 1099 | [86 empty] | 1099
[44 empty] | 1100 | [87 empty] | 1100 | [86 empty] | 1100
[44 empty] | 1101 | [87 empty] | 1101 | [86 empty] | 1101
[44 empty] | 1102 | [87 empty] | 1102 | [86 empty] | 1102
[44 empty] | 1103 | [87 empty] | 1103 | [86 empty] | 1103
[44 empty] | 1104 | [87 empty] | 1104 | [86 empty] | 1104
[44 empty] | 1105 | [87 empty] | 1105 | [86 empty] | 1105
[44 empty] | 1106 | [87 empty] | 1106 | [86 empty] | 1106
[44 empty] | 1107 | [87 empty] | 1107 | [86 empty] | 1107
[44 empty] | 1108 | [87 empty] | 1108 | [86 empty] | 1108
[44 empty] | 1109 | [87 empty] | 1109 | [86 empty] | 1109
[44 empty] | 1110 | [87 empty] | 1110 | [86 empty] | 1110
[44 empty] | 1111 | [87 empty] | 1111 | [86 empty] | 1111
[44 empty] | 1112 | [87 empty] | 1112 | [86 empty] | 1112
[44 empty] | 1113 | [87 empty] | 1113 | [86 empty] | 1113
[44 empty] | 1114 | [87 empty] | 1114 | [86 empty] | 1114
[44 empty] | 1115 | [87 empty] | 1115 | [86 empty] | 1115
[44 empty] | 1116 | [87 empty] | 1116 | [86 empty] | 1116
[44 empty] | 1117 | [87 empty] | 1117 | [86 empty] | 1117
[44 empty] | 1118 | [87 empty] | 1118 | [86 empty] | 1118
[44 empty] | 1119 | [87 empty] | 1119 | [86 empty] | 1119
[44 empty] | 1120 | [87 empty] | 1120 | [86 empty] | 1120
[44 empty] | 1121 | [87 empty] | 1121 | [86 empty] | 1121
[44 empty] | 1122 | [87 empty] | 1122 | [86 empty] | 1122
[44 empty] | 1123 | [87 empty] | 1123 | [86 empty] | 1123
[44 empty] | 1124 | [87 empty] | 1124 | [86 empty] | 1124
[44 empty] | 1125 | [87 empty] | 1125 | [86 empty] | 1125
[44 empty] | 1126 | [87 empty] | 1126 | [86 empty] | 1126
[44 empty] | 1127 | [87 empty] | 1127 | [86 empty] | 1127
[44 empty] | 1128 | [87 empty] | 1128 | [86 empty] | 1128
[44 empty] | 1129 | [87 empty] | 1129 | [86 empty] | 1129
[44 empty] | 1130 | [87 empty] | 1130 | [86 empty] | 1130
[44 empty] | 1131 | [87 empty] | 1131 | [86 empty] | 1131
[44 empty] | 1132 | [87 empty] | 1132 | [86 empty] | 1132
[44 empty] | 1133 | [87 empty] | 1133 | [86 empty] | 1133
[44 empty] | 1134 | [87 empty] | 1134 | [86 empty] | 1134
[44 empty] | 1135 | [87 empty] | 1135 | [86 empty] | 1135
[44 empty] | 1136 | [87 empty] | 1136 | [86 empty] | 1136
[44 empty] | 1137 | [87 empty] | 1137 | [86 empty] | 1137
[44 empty] | 1138 | [87 empty] | 1138 | [86 empty] | 1138
[44 empty] | 1139 | [87 empty] | 1139 | [86 empty] | 1139
[44 empty] | 1140 | [87 empty] | 1140 | [86 empty] | 1140
[44 empty] | 1141 | [87 empty] | 1141 | [86 empty] | 1141
[44 empty] | 1142 | [87 empty] | 1142 | [86 empty] | 1142
[44 empty] | 1143 | [87 empty] | 1143 | [86 empty] | 1143
[44 empty] | 1144 | [87 empty] | 1144 | [86 empty] | 1144
[44 empty] | 1145 | [87 empty] | 1145 | [86 empty] | 1145
[44 empty] | 1146 | [87 empty] | 1146 | [86 empty] | 1146
[44 empty] | 1147 | [87 empty] | 1147 | [86 empty] | 1147
[44 empty] | 1148 | [87 empty] | 1148 | [86 empty] | 1148
[44 empty] | 1149 | [87 empty] | 1149 | [86 empty] | 1149
[44 empty] | 1150 | [87 empty] | 1150 | [86 empty] | 1150
[44 empty] | 1151 | [87 empty] | 1151 | [86 empty] | 1151
[44 empty] | 1152 | [87 empty] | 1152 | [86 empty] | 1152
[44 empty] | 1153 | [87 empty] | 1153 | [86 empty] | 1153
[44 empty] | 1154 | [87 empty] | 1154 | [86 empty] | 1154
[44 empty] | 1155 | [87 empty] | 1155 | [86 empty] | 1155
[44 empty] | 1156 | [87 empty] | 1156 | [86 empty] | 1156
[44 empty] | 1157 | [87 empty] | 1157 | [86 empty] | 1157
[44 empty] | 1158 | [87 empty] | 1158 | [86 empty] | 1158
[44 empty] | 1159 | [87 empty] | 1159 | [86 empty] | 1159
[44 empty] | 1160 | [87 empty] | 1160 | [86 empty] | 1160
[44 empty] | 1161 | [87 empty] | 1161 | [86 empty] | 1161
[44 empty] | 1162 | [87 empty] | 1162 | [86 empty] | 1162
[44 empty] | 1163 | [87 empty] | 1163 | [86 empty] | 1163
[44 empty] | 1164 | [87 empty] | 1164 | [86 empty] | 1164
[44 empty] | 1165 | [87 empty] | 1165 | [86 empty] | 1165
[44 empty] | 1166 | [87 empty] | 1166 | [86 empty] | 1166
[44 empty] | 1167 | [87 empty] | 1167 | [86 empty] | 1167
[44 empty] | 1168 | [87 empty] | 1168 | [86 empty] | 1168
[44 empty] | 1169 | [87 empty] | 1169 | [86 empty] | 1169
[44 empty] | 1170 | [87 empty] | 1170 | [86 empty] | 1170
[44 empty] | 1171 | [87 empty] | 1171 | [86 empty] | 1171
[44 empty] | 1172 | [87 empty] | 1172 | [86 empty] | 1172
[44 empty] | 1173 | [87 empty] | 1173 | [86 empty] | 1173
[44 empty] | 1174 | [87 empty] | 1174 | [86 empty] | 1174
[44 empty] | 1175 | [87 empty] | 1175 | [86 empty] | 1175
[44 empty] | 1176 | [87 empty] | 1176 | [86 empty] | 1176
[44 empty] | 1177 | [87 empty] | 1177 | [86 empty] | 1177
[44 empty] | 1178 | [87 empty] | 1178 | [86 empty] | 1178
[44 empty] | 1179 | [87 empty] | 1179 | [86 empty] | 1179
[44 empty] | 1180 | [87 empty] | 1180 | [86 empty] | 1180
[44 empty] | 1181 | [87 empty] | 1181 | [86 empty] | 1181
[44 empty] | 1182 | [87 empty] | 1182 | [86 empty] | 1182
[44 empty] | 1183 | [87 empty] | 1183 | [86 empty] | 1183
[44 empty] | 1184 | [87 empty] | 1184 | [86 empty] | 1184
[44 empty] | 1185 | [87 empty] | 1185 | [86 empty] | 1185
[44 empty] | 1186 | [87 empty] | 1186 | [86 empty] | 1186
[44 empty] | 1187 | [87 empty] | 1187 | [86 empty] | 1187
[44 empty] | 1188 | [87 empty] | 1188 | [86 empty] | 1188
[44 empty] | 1189 | [87 empty] | 1189 | [86 empty] | 1189
[44 empty] | 1190 | [87 empty] | 1190 | [86 empty] | 1190
[44 empty] | 1191 | [87 empty] | 1191 | [86 empty] | 1191
[44 empty] | 1192 | [87 empty] | 1192 | [86 empty] | 1192
[44 empty] | 1193 | [87 empty] | 1193 | [86 empty] | 1193
[44 empty] | 1194 | [87 empty] | 1194 | [86 empty] | 1194
[44 empty] | 1195 | [87 empty] | 1195 | [86 empty] | 1195
[44 empty] | 1196 | [87 empty] | 1196 | [86 empty] | 1196
[44 empty] | 1197 | [87 empty] | 1197 | [86 empty] | 1197
[44 empty] | 1198 | [87 empty] | 1198 | [86 empty] | 1198
[44 empty] | 1199 | [87 empty] | 1199 | [86 empty] | 1199
[44 empty] | 1200 | [87 empty] | 1200 | [86 empty] | 1200
[44 empty] | 1201 | [87 empty] | 1201 | [86 empty] | 1201
[44 empty] | 1202 | [87 empty] | 1202 | [86 empty] | 1202
[44 empty] | 1203 | [87 empty] | 1203 | [86 empty] | 1203
[44 empty] | 1204 | [87 empty] | 1204 | [86 empty] | 1204
[44 empty] | 1205 | [87 empty] | 1205 | [86 empty] | 1205
[44 empty] | 1206 | [87 empty] | 1206 | [86 empty] | 1206
[44 empty] | 1207 | [87 empty] | 1207 | [86 empty] | 1207
[44 empty] | 1208 | [87 empty] | 1208 | [86 empty] | 1208
[44 empty] | 1209 | [87 empty] | 1209 | [86 empty] | 1209
[44 empty] | 1210 | [87 empty] | 1210 | [86 empty] | 1210
[44 empty] | 1211 | [87 empty] | 1211 | [86 empty] | 1211
[44 empty] | 1212 | [87 empty] | 1212 | [86 empty] | 1212
[44 empty] | 1213 | [87 empty] | 1213 | [86 empty] | 1213
[44 empty] | 1214 | [87 empty] | 1214 | [86 empty] | 1214
[44 empty] | 1215 | [87 empty] | 1215 | [86 empty] | 1215
[44 empty] | 1216 | [87 empty] | 1216 | [86 empty] | 1216
[44 empty] | 1217 | [87 empty] | 1217 | [86 empty] | 1217
[44 empty] | 1218 | [87 empty] | 1218 | [86 empty] | 1218
[44 empty] | 1219 | [87 empty] | 1219 | [86 empty] | 1219
[44 empty] | 1220 | [87 empty] | 1220 | [86 empty] | 1220
[44 empty] | 1221 | [87 empty] | 1221 | [86 empty] | 1221
[44 empty] | 1222 | [87 empty] | 1222 | [86 empty] | 1222
[44 empty] | 1223 | [87 empty] | 1223 | [86 empty] | 1223
[44 empty] | 1224 | [87 empty] | 1224 | [86 empty] | 1224
[44 empty] | 1225 | [87 empty] | 1225 | [86 empty] | 1225
[44 empty] | 1226 | [87 empty] | 1226 | [86 empty] | 1226
[44 empty] | 1227 | [87 empty] | 1227 | [86 empty] | 1227
[44 empty] | 1228 | [87 empty] | 1228 | [86 empty] | 1228
[44 empty] | 1229 | [87 empty] | 1229 | [86 empty] | 1229
[44 empty] | 1230 | [87 empty] | 1230 | [86 empty] | 1230
[44 empty] | 1231 | [87 empty] | 1231 | [86 empty] | 1231
[44 empty] | 1232 | [87 empty] | 1232 | [86 empty] | 1232
[44 empty] | 1233 | [87 empty] | 1233 | [86 empty] | 1233
[44 empty] | 1234 | [87 empty] | 1234 | [86 empty] | 1234
[44 empty] | 1235 | [87 empty] | 1235 | [86 empty] | 1235
[44 empty] | 1236 | [87 empty] | 1236 | [86 empty] | 1236
[44 empty] | 1237 | [87 empty] | 1237 | [86 empty] | 1237
[44 empty] | 1238 | [87 empty] | 1238 | [86 empty] | 1238
[44 empty] | 1239 | [87 empty] | 1239 | [86 empty] | 1239
[44 empty] | 1240 | [87 empty] | 1240 | [86 empty] | 1240
[44 empty] | 1241 | [87 empty] | 1241 | [86 empty] | 1241
[44 empty] | 1242 | [87 empty] | 1242 | [86 empty] | 1242
[44 empty] | 1243 | [87 empty] | 1243 | [86 empty] | 1243
[44 empty] | 1244 | [87 empty] | 1244 | [86 empty] | 1244
[44 empty] | 1245 | [87 empty] | 1245 | [86 empty] | 1245
[44 empty] | 1246 | [87 empty] | 1246 | [86 empty] | 1246
[44 empty] | 1247 | [87 empty] | 1247 | [86 empty] | 1247
[44 empty] | 1248 | [87 empty] | 1248 | [86 empty] | 1248
[44 empty] | 1249 | [87 empty] | 1249 | [86 empty] | 1249
[44 empty] | 1250 | [87 empty] | 1250 | [86 empty] | 1250
[44 empty] | 1251 | [87 empty] | 1251 | [86 empty] | 1251
[44 empty] | 1252 | [87 empty] | 1252 | [86 empty] | 1252
[44 empty] | 1253 | [87 empty] | 1253 | [86 empty] | 1253
[44 empty] | 1254 | [87 empty] | 1254 | [86 empty] | 1254
[44 empty] | 1255 | [87 empty] | 1255 | [86 empty] | 1255
[44 empty] | 1256 | [87 empty] | 1256 | [86 empty] | 1256
[44 empty] | 1257 | [87 empty] | 1257 | [86 empty] | 1257
[44 empty] | 1258 | [87 empty] | 1258 | [86 empty] | 1258
[44 empty] | 1259 | [87 empty] | 1259 | [86 empty] | 1259
[44 empty] | 1260 | [87 empty] | 1260 | [86 empty] | 1260
[44 empty] | 1261 | [87 empty] | 1261 | [86 empty] | 1261
[44 empty] | 1262 | [87 empty] | 1262 | [86 empty] | 1262
[44 empty] | 1263 | [87 empty] | 1263 | [86 empty] | 1263
[44 empty] | 1264 | [87 empty] | 1264 | [86 empty] | 1264
[44 empty] | 1265 | [87 empty] | 1265 | [86 empty] | 1265
[44 empty] | 1266 | [87 empty] | 1266 | [86 empty] | 1266
[44 empty] | 1267 | [87 empty] | 1267 | [86 empty] | 1267
[44 empty] | 1268 | [87 empty] | 1268 | [86 empty] | 1268
[44 empty] | 1269 | [87 empty] | 1269 | [86 empty] | 1269
[44 empty] | 1270 | [87 empty] | 1270 | [86 empty] | 1270
[44 empty] | 1271 | [87 empty] | 1271 | [86 empty] | 1271
[44 empty] | 1272 | [87 empty] | 1272 | [86 empty] | 1272
[44 empty] | 1273 | [87 empty] | 1273 | [86 empty] | 1273
[44 empty] | 1274 | [87 empty] | 1274 | [86 empty] | 1274
[44 empty] | 1275 | [87 empty] | 1275 | [86 empty] | 1275
[44 empty] | 1276 | [87 empty] | 1276 | [86 empty] | 1276
[44 empty] | 1277 | [87 empty] | 1277 | [86 empty] | 1277
[44 empty] | 1278 | [87 empty] | 1278 | [86 empty] | 1278
[44 empty] | 1279 | [87 empty] | 1279 | [86 empty] | 1279
[44 empty] | 1280 | [87 empty] | 1280 | [86 empty] | 1280
[44 empty] | 1281 | [87 empty] | 1281 | [86 empty] | 1281
[44 empty] | 1282 | [87 empty] | 1282 | [86 empty] | 1282
[44 empty] | 1283 | [87 empty] | 1283 | [86 empty] | 1283
[44 empty] | 1284 | [87 empty] | 1284 | [86 empty] | 1284
[44 empty] | 1285 | [87 empty] | 1285 | [86 empty] | 1285
[44 empty] | 1286 | [87 empty] | 1286 | [86 empty] | 1286
[44 empty] | 1287 | [87 empty] | 1287 | [86 empty] | 1287
[44 empty] | 1288 | [87 empty] | 1288 | [86 empty] | 1288
[44 empty] | 1289 | [87 empty] | 1289 | [86 empty] | 1289
[44 empty] | 1290 | [87 empty] | 1290 | [86 empty] | 1290
[44 empty] | 1291 | [87 empty] | 1291 | [86 empty] | 1291
[44 empty] | 1292 | [87 empty] | 1292 | [86 empty] | 1292
[44 empty] | 1293 | [87 empty] | 1293 | [86 empty] | 1293
[44 empty] | 1294 | [87 empty] | 1294 | [86 empty] | 1294
[44 empty] | 1295 | [87 empty] | 1295 | [86 empty] | 1295
[44 empty] | 1296 | [87 empty] | 1296 | [86 empty] | 1296
[44 empty] | 1297 | [87 empty] | 1297 | [86 empty] | 1297
[44 empty] | 1298 | [87 empty] | 1298 | [86 empty] | 1298
[44 empty] | 1299 | [87 empty] | 1299 | [86 empty] | 1299
[44 empty] | 1300 | [87 empty] | 1300 | [86 empty] | 1300
[44 empty] | 1301 | [87 empty] | 1301 | [86 empty] | 1301
[44 empty] | 1302 | [87 empty] | 1302 | [86 empty] | 1302
[44 empty] | 1303 | [87 empty] | 1303 | [86 empty] | 1303
[44 empty] | 1304 | [87 empty] | 1304 | [86 empty] | 1304
[44 empty] | 1305 | [87 empty] | 1305 | [86 empty] | 1305
[44 empty] | 1306 | [87 empty] | 1306 | [86 empty] | 1306
[44 empty] | 1307 | [87 empty] | 1307 | [86 empty] | 1307
[44 empty] | 1308 | [87 empty] | 1308 | [86 empty] | 1308
[44 empty] | 1309 | [87 empty] | 1309 | [86 empty] | 1309
[44 empty] | 1310 | [87 empty] | 1310 | [86 empty] | 1310
[44 empty] | 1311 | [87 empty] | 1311 | [86 empty] | 1311
[44 empty] | 1312 | [87 empty] | 1312 | [86 empty] | 1312
[44 empty] | 1313 | [87 empty] | 1313 | [86 empty] | 1313
[44 empty] | 1314 | [87 empty] | 1314 | [86 empty] | 1314
[44 empty] | 1315 | [87 empty] | 1315 | [86 empty] | 1315
[44 empty] | 1316 | [87 empty] | 1316 | [86 empty] | 1316
[44 empty] | 1317 | [87 empty] | 1317 | [86 empty] | 1317
[44 empty] | 1318 | [87 empty] | 1318 | [86 empty] | 1318
[44 empty] | 1319 | [87 empty] | 1319 | [86 empty] | 1319
[44 empty] | 1320 | [87 empty] | 1320 | [86 empty] | 1320
[44 empty] | 1321 | [87 empty] | 1321 | [86 empty] | 1321
[44 empty] | 1322 | [87 empty] | 1322 | [86 empty] | 1322
[44 empty] | 1323 | [87 empty] | 1323 | [86 empty] | 1323
[44 empty] | 1324 | [87 empty] | 1324 | [86 empty] | 1324
[44 empty] | 1325 | [87 empty] | 1325 | [86 empty] | 1325
[44 empty] | 1326 | [87 empty] | 1326 | [86 empty] | 1326
[44 empty] | 1327 | [87 empty] | 1327 | [86 empty] | 1327
[44 empty] | 1328 | [87 empty] | 1328 | [86 empty] | 1328
[44 empty] | 1329 | [87 empty] | 1329 | [86 empty] | 1329
[44 empty] | 1330 | [87 empty] | 1330 | [86 empty] | 1330
[44 empty] | 1331 | [87 empty] | 1331 | [86 empty] | 1331
[44 empty] | 1332 | [87 empty] | 1332 | [86 empty] | 1332
[44 empty] | 1333 | [87 empty] | 1333 | [86 empty] | 1333
[44 empty] | 1334 | [87 empty] | 1334 | [86 empty] | 1334
[44 empty] | 1335 | [87 empty] | 1335 | [86 empty] | 1335
[44 empty] | 1336 | [87 empty] | 1336 | [86 empty] | 1336
[44 empty] | 1337 | [87 empty] | 1337 | [86 empty] | 1337
[44 empty] | 1338 | [87 empty] | 1338 | [86 empty] | 1338
[44 empty] | 1339 | [87 empty] | 1339 | [86 empty] | 1339
[44 empty] | 1340 | [87 empty] | 1340 | [86 empty] | 1340
[44 empty] | 1341 | [87 empty] | 1341 | [86 empty] | 1341
[44 empty] | 1342 | [87 empty] | 1342 | [86 empty] | 1342
[44 empty] | 1343 | [87 empty] | 1343 | [86 empty] | 1343
[44 empty] | 1344 | [87 empty] | 1344 | [86 empty] | 1344
[44 empty] | 1345 | [87 empty] | 1345 | [86 empty] | 1345
[44 empty] | 1346 | [87 empty] | 1346 | [86 empty] | 1346
[44 empty] | 1347 | [87 empty] | 1347 | [86 empty] | 1347
[44 empty] | 1348 | [87 empty] | 1348 | [86 empty] | 1348
[44 empty] | 1349 | [87 empty] | 1349 | [86 empty] | 1349
[44 empty] | 1350 | [87 empty] | 1350 | [86 empty] | 1350
[44 empty] | 1351 | [87 empty] | 1351 | [86 empty] | 1351
[44 empty] | 1352 | [87 empty] | 1352 | [86 empty] | 1352
[44 empty] | 1353 | [87 empty] | 1353 | [86 empty] | 1353
[44 empty] | 1354 | [87 empty] | 1354 | [86 empty] | 1354
[44 empty] | 1355 | [87 empty] | 1355 | [86 empty] | 1355
[44 empty] | 1356 | [87 empty] | 1356 | [86 empty] | 1356
[44 empty] | 1357 | [87 empty] | 1357 | [86 empty] | 1357
[44 empty] | 1358 | [87 empty] | 1358 | [86 empty] | 1358
[44 empty] | 1359 | [87 empty] | 1359 | [86 empty] | 1359
[44 empty] | 1360 | [87 empty] | 1360 | [86 empty] | 1360
[44 empty] | 1361 | [87 empty] | 1361 | [86 empty] | 1361
[44 empty] | 1362 | [87 empty] | 1362 | [86 empty] | 1362
[44 empty] | 1363 | [87 empty] | 1363 | [86 empty] | 1363
[44 empty] | 1364 | [87 empty] | 1364 | [86 empty] | 1364
[44 empty] | 1365 | [87 empty] | 1365 | [86 empty] | 1365
[44 empty] | 1366 | [87 empty] | 1366 | [86 empty] | 1366
[44 empty] | 1367 | [87 empty] | 1367 | [86 empty] | 1367
[44 empty] | 1368 | [87 empty] | 1368 | [86 empty] | 1368
[44 empty] | 1369 | [87 empty] | 1369 | [86 empty] | 1369
[44 empty] | 1370 | [87 empty] | 1370 | [86 empty] | 1370
[44 empty] | 1371 | [87 empty] | 1371 | [86 empty] | 1371
[44 empty] | 1372 | [87 empty] | 1372 | [86 empty] | 1372
[44 empty] | 1373 | [87 empty] | 1373 | [86 empty] | 1373
[44 empty] | 1374 | [87 empty] | 1374 | [86 empty] | 1374
[44 empty] | 1375 | [87 empty] | 1375 | [86 empty] | 1375
[44 empty] | 1376 | [87 empty] | 1376 | [86 empty] | 1376
[44 empty] | 1377 | [87 empty] | 1377 | [86 empty] | 1377
[44 empty] | 1378 | [87 empty] | 1378 | [86 empty] | 1378
[44 empty] | 1379 | [87 empty] | 1379 | [86 empty] | 1379
[44 empty] | 1380 | [87 empty] | 1380 | [86 empty] | 1380
[44 empty] | 1381 | [87 empty] | 1381 | [86 empty] | 1381
[44 empty] | 1382 | [87 empty] | 1382 | [86 empty] | 1382
[44 empty] | 1383 | [87 empty] | 1383 | [86 empty] | 1383
[44 empty] | 1384 | [87 empty] | 1384 | [86 empty] | 1384
[44 empty] | 1385 | [87 empty] | 1385 | [86 empty] | 1385
[44 empty] | 1386 | [87 empty] | 1386 | [86 empty] | 1386
[44 empty] | 1387 | [87 empty] | 1387 | [86 empty] | 1387
[44 empty] | 1388 | [87 empty] | 1388 | [86 empty] | 1388
[44 empty] | 1389 | [87 empty] | 1389 | [86 empty] | 1389
[44 empty] | 1390 | [87 empty] | 1390 | [86 empty] | 1390
[44 empty] | 1391 | [87 empty] | 1391 | [86 empty] | 1391
[44 empty] | 1392 | [87 empty] | 1392 | [86 empty] | 1392
[44 empty] | 1393 | [87 empty] | 1393 | [86 empty] | 1393
[44 empty] | 1394 | [87 empty] | 1394 | [86 empty] | 1394
[44 empty] | 1395 | [87 empty] | 1395 | [86 empty] | 1395
[44 empty] | 1396 | [87 empty] | 1396 | [86 empty] | 1396
[44 empty] | 1397 | [87 empty] | 1397 | [86 empty] | 1397
[44 empty] | 1398 | [87 empty] | 1398 | [86 empty] | 1398
[44 empty] | 1399 | [87 empty] | 1399 | [86 empty] | 1399
[44 empty] | 1400 | [87 empty] | 1400 | [86 empty] | 1400
[44 empty] | 1401 | [87 empty] | 1401 | [86 empty] | 1401
[44 empty] | 1402 | [87 empty] | 1402 | [86 empty] | 1402
[44 empty] | 1403 | [87 empty] | 1403 | [86 empty] | 1403
[44 empty] | 1404 | [87 empty] | 1404 | [86 empty] | 1404
[44 empty] | 1405 | [87 empty] | 1405 | [86 empty] | 1405
[44 empty] | 1406 | [87 empty] | 1406 | [86 empty] | 1406
[44 empty] | 1407 | [87 empty] | 1407 | [86 empty] | 1407
[44 empty] | 1408 | [87 empty] | 1408 | [86 empty] | 1408
[44 empty] | 1409 | [87 empty] | 1409 | [86 empty] | 1409
[44 empty] | 1410 | [87 empty] | 1410 | [86 empty] | 1410
[44 empty] | 1411 | [87 empty] | 1411 | [86 empty] | 1411
[44 empty] | 1412 | [87 empty] | 1412 | [86 empty] | 1412
[44 empty] | 1413 | [87 empty] | 1413 | [86 empty] | 1413
[44 empty] | 1414 | [87 empty] | 1414 | [86 empty] | 1414
[44 empty] | 1415 | [87 empty] | 1415 | [86 empty] | 1415
[44 empty] | 1416 | [87 empty] | 1416 | [86 empty] | 1416
[44 empty] | 1417 | [87 empty] | 1417 | [86 empty] | 1417
[44 empty] | 1418 | [87 empty] | 1418 | [86 empty] | 1418
[44 empty] | 1419 | [87 empty] | 1419 | [86 empty] | 1419
[44 empty] | 1420 | [87 empty] | 1420 | [86 empty] | 1420
[44 empty] | 1421 | [87 empty] | 1421 | [86 empty] | 1421
[44 empty] | 1422 | [87 empty] | 1422 | [86 empty] | 1422
[44 empty] | 1423 | [87 empty] | 1423 | [86 empty] | 1423
[44 empty] | 1424 | [87 empty] | 1424 | [86 empty] | 1424
[44 empty] | 1425 | [87 empty] | 1425 | [86 empty] | 1425
[44 empty] | 1426 | [87 empty] | 1426 | [86 empty] | 1426
[44 empty] | 1427 | [87 empty] | 1427 | [86 empty] | 1427
[44 empty] | 1428 | [87 empty] | 1428 | [86 empty] | 1428
[44 empty] | 1429 | [87 empty] | 1429 | [86 empty] | 1429
[44 empty] | 1430 | [87 empty] | 1430 | [86 empty] | 1430
[44 empty] | 1431 | [87 empty] | 1431 | [86 empty] | 1431
[44 empty] | 1432 | [87 empty] | 1432 | [86 empty] | 1432
[44 empty] | 1433 | [87 empty] | 1433 | [86 empty] | 1433
[44 empty] | 1434 | [87 empty] | 1434 | [86 empty] | 1434
[44 empty] | 1435 | [87 empty] | 1435 | [86 empty] | 1435
[44 empty] | 1436 | [87 empty] | 1436 | [86 empty] | 1436
[44 empty] | 1437 | [87 empty] | 1437 | [86 empty] | 1437
[44 empty] | 1438 | [87 empty] | 1438 | [86 empty] | 1438
[44 empty] | 1439 | [87 empty] | 1439 | [86 empty] | 1439
[44 empty] | 1440 | [87 empty] | 1440 | [86 empty] | 1440
[44 empty] | 1441 | [87 empty] | 1441 | [86 empty] | 1441
[44 empty] | 1442 | [87 empty] | 1442 | [86 empty] | 1442
[44 empty] | 1443 | [87 empty] | 1443 | [86 empty] | 1443
[44 empty] | 1444 | [87 empty] | 1444 | [86 empty] | 1444
[44 empty] | 1445 | [87 empty] | 1445 | [86 empty] | 1445
[44 empty] | 1446 | [87 empty] | 1446 | [86 empty] | 1446
[44 empty] | 1447 | [87 empty] | 1447 | [86 empty] | 1447
[44 empty] | 1448 | [87 empty] | 1448 | [86 empty] | 1448
[44 empty] | 1449 | [87 empty] | 1449 | [86 empty] | 1449
[44 empty] | 1450 | [87 empty] | 1450 | [86 empty] | 1450
[44 empty] | 1451 | [87 empty] | 1451 | [86 empty] | 1451
[44 empty] | 1452 | [87 empty] | 1452 | [86 empty] | 1452
[44 empty] | 1453 | [87 empty] | 1453 | [86 empty] | 1453
[44 empty] | 1454 | [87 empty] | 1454 | [86 empty] | 1454
[44 empty] | 1455 | [87 empty] | 1455 | [86 empty] | 1455
[44 empty] | 1456 | [87 empty] | 1456 | [86 empty] | 1456
[44 empty] | 1457 | [87 empty] | 1457 | [86 empty] | 1457
[44 empty] | 1458 | [87 empty] | 1458 | [86 empty] | 1458
[44 empty] | 1459 | [87 empty] | 1459 | [86 empty] | 1459
[44 empty] | 1460 | [87 empty] | 1460 | [86 empty] | 1460
[44 empty] | 1461 | [87 empty] | 1461 | [86 empty] | 1461
[44 empty] | 1462 | [87 empty] | 1462 | [86 empty] | 1462
[44 empty] | 1463 | [87 empty] | 1463 | [86 empty] | 1463
[44 empty] | 1464 | [87 empty] | 1464 | [86 empty] | 1464
[44 empty] | 1465 | [87 empty] | 1465 | [86 empty] | 1465
[44 empty] | 1466 | [87 empty] | 1466 | [86 empty] | 1466
[44 empty] | 1467 | [87 empty] | 1467 | [86 empty] | 1467
[44 empty] | 1468 | [87 empty] | 1468 | [86 empty] | 1468
[44 empty] | 1469 | [87 empty] | 1469 | [86 empty] | 1469
[44 empty] | 1470 | [87 empty] | 1470 | [86 empty] | 1470
[44 empty] | 1471 | [87 empty] | 1471 | [86 empty] | 1471
[44 empty] | 1472 | [87 empty] | 1472 | [86 empty] | 1472
[44 empty] | 1473 | [87 empty] | 1473 | [86 empty] | 1473
[44 empty] | 1474 | [87 empty] | 1474 | [86 empty] | 1474
[44 empty] | 1475 | [87 empty] | 1475 | [86 empty] | 1475
[44 empty] | 1476 | [87 empty] | 1476 | [86 empty] | 1476
[44 empty] | 1477 | [87 empty] | 1477 | [86 empty] | 1477
[44 empty] | 1478 | [87 empty] | 1478 | [86 empty] | 1478
[44 empty] | 1479 | [87 empty] | 1479 | [86 empty] | 1479
[44 empty] | 1480 | [87 empty] | 1480 | [86 empty] | 1480
[44 empty] | 1481 | [87 empty] | 1481 | [86 empty] | 1481
[44 empty] | 1482 | [87 empty] | 1482 | [86 empty] | 1482
[44 empty] | 1483 | [87 empty] | 1483 | [86 empty] | 1483
[44 empty] | 1484 | [87 empty] | 1484 | [86 empty] | 1484
[44 empty] | 1485 | [87 empty] | 1485 | [86 empty] | 1485
[44 empty] | 1486 | [87 empty] | 1486 | [86 empty] | 1486
[44 empty] | 1487 | [87 empty] | 1487 | [86 empty] | 1487
[44 empty] | 1488 | [87 empty] | 1488 | [86 empty] | 1488
[44 empty] | 1489 | [87 empty] | 1489 | [86 empty] | 1489
[44 empty] | 1490 | [87 empty] | 1490 | [86 empty] | 1490
[44 empty] | 1491 | [87 empty] | 1491 | [86 empty] | 1491
[44 empty] | 1492 | [87 empty] | 1492 | [86 empty] | 1492
[44 empty] | 1493 | [87 empty] | 1493 | [86 empty] | 1493
[44 empty] | 1494 | [87 empty] | 1494 | [86 empty] | 1494
[44 empty] | 1495 | [87 empty] | 1495 | [86 empty] | 1495
[44 empty] | 1496 | [87 empty] | 1496 | [86 empty] | 1496
[44 empty] | 1497 | [87 empty] | 1497 | [86 empty] | 1497
[44 empty] | 1498 | [87 empty] | 1498 | [86 empty] | 1498
[44 empty] | 1499 | [87 empty] | 1499 | [86 empty] | 1499
[44 empty] | 1500 | [87 empty] | 1500 | [86 empty] | 1500
[44 empty] | 1501 | [87 empty] | 1501 | [86 empty] | 1501
[44 empty] | 1502 | [87 empty] | 1502 | [86 empty] | 1502
[44 empty] | 1503 | [87 empty] | 1503 | [86 empty] | 1503
[44 empty] | 1504 | [87 empty] | 1504 | [86 empty] | 1504
[44 empty] | 1505 | [87 empty] | 1505 | [86 empty] | 1505
[44 empty] | 1506 | [87 empty] | 1506 | [86 empty] | 1506
[44 empty] | 1507 | [87 empty] | 1507 | [86 empty] | 1507
[44 empty] | 1508 | [87 empty] | 1508 | [86 empty] | 1508
[44 empty] | 1509 | [87 empty] | 1509 | [86 empty] | 1509
[44 empty] | 1510 | [87 empty] | 1510 | [86 empty] | 1510
[44 empty] | 1511 | [87 empty] | 1511 | [86 empty] | 1511
[44 empty] | 1512 | [87 empty] | 1512 | [86 empty] | 1512
[44 empty] | 1513 | [87 empty] | 1513 | [86 empty] | 1513
[44 empty] | 1514 | [87 empty] | 1514 | [86 empty] | 1514
[44 empty] | 1515 | [87 empty] | 1515 | [86 empty] | 1515
[44 empty] | 1516 | [87 empty] | 1516 | [86 empty] | 1516
[44 empty] | 1517 | [87 empty] | 1517 | [86 empty] | 1517
[44 empty] | 1518 | [87 empty] | 1518 | [86 empty] | 1518
[44 empty] | 1519 | [87 empty] | 1519 | [86 empty] | 1519
[44 empty] | 1520 | [87 empty] | 1520 | [86 empty] | 1520
[44 empty] | 1521 | [87 empty] | 1521 | [86 empty] | 1521
[44 empty] | 1522 | [87 empty] | 1522 | [86 empty] | 1522
[44 empty] | 1523 | [87 empty] | 1523 | [86 empty] | 1523
[44 empty] | 1524 | [87 empty] | 1524 | [86 empty] | 1524
[44 empty] | 1525 | [87 empty] | 1525 | [86 empty] | 1525
[44 empty] | 1526 | [87 empty] | 1526 | [86 empty] | 1526
[44 empty] | 1527 | [87 empty] | 1527 | [86 empty] | 1527
[44 empty] | 1528 | [87 empty] | 1528 | [86 empty] | 1528
[44 empty] | 1529 | [87 empty] | 1529 | [86 empty] | 1529
[44 empty] | 1530 | [87 empty] | 1530 | [86 empty] | 1530
[44 empty] | 1531 | [87 empty] | 1531 | [86 empty] | 1531
[44 empty] | 1532 | [87 empty] | 1532 | [86 empty] | 1532
[44 empty] | 1533 | [87 empty] | 1533 | [86 empty] | 1533
[44 empty] | 1534 | [87 empty] | 1534 | [86 empty] | 1534
[44 empty] | 1535 | [87 empty] | 1535 | [86 empty] | 1535
[44 empty] | 1536 | [87 empty] | 1536 | [86 empty] | 1536
[44 empty] | 1537 | [87 empty] | 1537 | [86 empty] | 1537
[44 empty] | 1538 | [87 empty] | 1538 | [86 empty] | 1538
[44 empty] | 1539 | [87 empty] | 1539 | [86 empty] | 1539
[44 empty] | 1540 | [87 empty] | 1540 | [86 empty] | 1540
[44 empty] | 1541 | [87 empty] | 1541 | [86 empty] | 1541
[44 empty] | 1542 | [87 empty] | 1542 | [86 empty] | 1542
[44 empty] | 1543 | [87 empty] | 1543 | [86 empty] | 1543
[44 empty] | 1544 | [87 empty] | 1544 | [86 empty] | 1544
[44 empty] | 1545 | [87 empty] | 1545 | [86 empty] | 1545
[44 empty] | 1546 | [87 empty] | 1546 | [86 empty] | 1546
[44 empty] | 1547 | [87 empty] | 1547 | [86 empty] | 1547
[44 empty] | 1548 | [87 empty] | 1548 | [86 empty] | 1548
[44 empty] | 1549 | [87 empty] | 1549 | [86 empty] | 1549
[44 empty] | 1550 | [87 empty] | 1550 | [86 empty] | 1550
[44 empty] | 1551 | [87 empty] | 1551 | [86 empty] | 1551
[44 empty] | 1552 | [87 empty] | 1552 | [86 empty] | 1552
[44 empty] | 1553 | [87 empty] | 1553 | [86 empty] | 1553
[44 empty] | 1554 | [87 empty] | 1554 | [86 empty] | 1554
[44 empty] | 1555 | [87 empty] | 1555 | [86 empty] | 1555
[44 empty] | 1556 | [87 empty] | 1556 | [86 empty] | 1556
[44 empty] | 1557 | [87 empty] | 1557 | [86 empty] | 1557
[44 empty] | 1558 | [87 empty] | 1558 | [86 empty] | 1558
[44 empty] | 1559 | [87 empty] | 1559 | [86 empty] | 1559
[44 empty] | 1560 | [87 empty] | 1560 | [86 empty] | 1560
[44 empty] | 1561 | [87 empty] | 1561 | [86 empty] | 1561
[44 empty] | 1562 | [87 empty] | 1562 | [86 empty] | 1562
[44 empty] | 1563 | [87 empty] | 1563 | [86 empty] | 1563
[44 empty] | 1564 | [87 empty] | 1564 | [86 empty] | 1564
[44 empty] | 1565 | [87 empty] | 1565 | [86 empty] | 1565
[44 empty] | 1566 | [87 empty] | 1566 | [86 empty] | 1566
[44 empty] | 1567 | [87 empty] | 1567 | [86 empty] | 1567
[44 empty] | 1568 | [87 empty] | 1568 | [86 empty] | 1568
[44 empty] | 1569 | [87 empty] | 1569 | [86 empty] | 1569
[44 empty] | 1570 | [87 empty] | 1570 | [86 empty] | 1570
[44 empty] | 1571 | [87 empty] | 1571 | [86 empty] | 1571
[44 empty] | 1572 | [87 empty] | 1572 | [86 empty] | 1572
[44 empty] | 1573 | [87 empty] | 1573 | [86 empty] | 1573
[44 empty] | 1574 | [87 empty] | 1574 | [86 empty] | 1574
[44 empty] | 1575 | [87 empty] | 1575 | [86 empty] | 1575
[44 empty] | 1576 | [87 empty] | 1576 | [86 empty] | 1576
[44 empty] | 1577 | [87 empty] | 1577 | [86 empty] | 1577
[44 empty] | 1578 | [87 empty] | 1578 | [86 empty] | 1578
[44 empty] | 1579 | [87 empty] | 1579 | [86 empty] | 1579
[44 empty] | 1580 | [87 empty] | 1580 | [86 empty] | 1580
[44 empty] | 1581 | [87 empty] | 1581 | [86 empty] | 1581
[44 empty] | 1582 | [87 empty] | 1582 | [86 empty] | 1582
[44 empty] | 1583 | [87 empty] | 1583 | [86 empty] | 1583
[44 empty] | 1584 | [87 empty] | 1584 | [86 empty] | 1584
[44 empty] | 1585 | [87 empty] | 1585 | [86 empty] | 1585
[44 empty] | 1586 | [87 empty] | 1586 | [86 empty] | 1586
[44 empty] | 1587 | [87 empty] | 1587 | [86 empty] | 1587
[44 empty] | 1588 | [87 empty] | 1588 | [86 empty] | 1588
[44 empty] | 1589 | [87 empty] | 1589 | [86 empty] | 1589
[44 empty] | 1590 | [87 empty] | 1590 | [86 empty] | 1590
[44 empty] | 1591 | [87 empty] | 1591 | [86 empty] | 1591
[44 empty] | 1592 | [87 empty] | 1592 | [86 empty] | 1592
[44 empty] | 1593 | [87 empty] | 1593 | [86 empty] | 1593
[44 empty] | 1594 | [87 empty] | 1594 | [86 empty] | 1594
[44 empty] | 1595 | [87 empty] | 1595 | [86 empty] | 1595
[44 empty] | 1596 | [87 empty] | 1596 | [86 empty] | 1596
[44 empty] | 1597 | [87 empty] | 1597 | [86 empty] | 1597
[44 empty] | 1598 | [87 empty] | 1598 | [86 empty] | 1598
[44 empty] | 1599 | [87 empty] | 1599 | [86 empty] | 1599
[44 empty] | 1600 | [87 empty] | 1600 | [86 empty] | 1600
[44 empty] | 1601 | [87 empty] | 1601 | [86 empty] | 1601
[44 empty] | 1602 | [87 empty] | 1602 | [86 empty] | 1602
[44 empty] | 1603 | [87 empty] | 1603 | [86 empty] | 1603
[44 empty] | 1604 | [87 empty] | 1604 | [86 empty] | 1604
[44 empty] | 1605 | [87 empty] | 1605 | [86 empty] | 1605
[44 empty] | 1606 | [87 empty] | 1606 | [86 empty] | 1606
[44 empty] | 1607 | [87 empty] | 1607 | [86 empty] | 1607
[44 empty] | 1608 | [87 empty] | 1608 | [86 empty] | 1608
[44 empty] | 1609 | [87 empty] | 1609 | [86 empty] | 1609
[44 empty] | 1610 | [87 empty] | 1610 | [86 empty] | 1610
[44 empty] | 1611 | [87 empty] | 1611 | [86 empty] | 1611
[44 empty] | 1612 | [87 empty] | 1612 | [86 empty] | 1612
[44 empty] | 1613 | [87 empty] | 1613 | [86 empty] | 1613
[44 empty] | 1614 | [87 empty] | 1614 | [86 empty] | 1614
[44 empty] | 1615 | [87 empty] | 1615 | [86 empty] | 1615
[44 empty] | 1616 | [87 empty] | 1616 | [86 empty] | 1616
[44 empty] | 1617 | [87 empty] | 1617 | [86 empty] | 1617
[44 empty] | 1618 | [87 empty] | 1618 | [86 empty] | 1618
[44 empty] | 1619 | [87 empty] | 1619 | [86 empty] | 1619
[44 empty] | 1620 | [87 empty] | 1620 | [86 empty] | 1620
[44 empty] | 1621 | [87 empty] | 1621 | [86 empty] | 1621
[44 empty] | 1622 | [87 empty] | 1622 | [86 empty] | 1622
[44 empty] | 1623 | [87 empty] | 1623 | [86 empty] | 1623
[44 empty] | 1624 | [87 empty] | 1624 | [86 empty] | 1624
[44 empty] | 1625 | [87 empty] | 1625 | [86 empty] | 1625
[44 empty] | 1626 | [87 empty] | 1626 | [86 empty] | 1626
[44 empty] | 1627 | [87 empty] | 1627 | [86 empty] | 1627
[44 empty] | 1628 | [87 empty] | 1628 | [86 empty] | 1628
[44 empty] | 1629 | [87 empty] | 1629 | [86 empty] | 1629
[44 empty] | 1630 | [87 empty] | 1630 | [86 empty] | 1630
[44 empty] | 1631 | [87 empty] | 1631 | [86 empty] | 1631
[44 empty] | 1632 | [87 empty] | 1632 | [86 empty] | 1632
[44 empty] | 1633 | [87 empty] | 1633 | [86 empty] | 1633
[44 empty] | 1634 | [87 empty] | 1634 | [86 empty] | 1634
[44 empty] | 1635 | [87 empty] | 1635 | [86 empty] | 1635
[44 empty] | 1636 | [87 empty] | 1636 | [86 empty] | 1636
[44 empty] | 1637 | [87 empty] | 1637 | [86 empty] | 1637
[44 empty] | 1638 | [87 empty] | 1638 | [86 empty] | 1638
[44 empty] | 1639 | [87 empty] | 1639 | [86 empty] | 1639
[44 empty] | 1640 | [87 empty] | 1640 | [86 empty] | 1640
[44 empty] | 1641 | [87 empty] | 1641 | [86 empty] | 1641
[44 empty] | 1642 | [87 empty] | 1642 | [86 empty] | 1642
[44 empty] | 1643 | [87 empty] | 1643 | [86 empty] | 1643
[44 empty] | 1644 | [87 empty] | 1644 | [86 empty] | 1644
[44 empty] | 1645 | [87 empty] | 1645 | [86 empty] | 1645
[44 empty] | 1646 | [87 empty] | 1646 | [86 empty] | 1646
[44 empty] | 1647 | [87 empty] | 1647 | [86 empty] | 1647
[44 empty] | 1648 | [87 empty] | 1648 | [86 empty] | 1648
[44 empty] | 1649 | [87 empty] | 1649 | [86 empty] | 1649
[44 empty] | 1650 | [87 empty] | 1650 | [86 empty] | 1650
[44 empty] | 1651 | [87 empty] | 1651 | [86 empty] | 1651
[44 empty] | 1652 | [87 empty] | 1652 | [86 empty] | 1652
[44 empty] | 1653 | [87 empty] | 1653 | [86 empty] | 1653
[44 empty] | 1654 | [87 empty] | 1654 | [86 empty] | 1654
[44 empty] | 1655 | [87 empty] | 1655 | [86 empty] | 1655
[44 empty] | 1656 | [87 empty] | 1656 | [86 empty] | 1656
[44 empty] | 1657 | [87 empty] | 1657 | [86 empty] | 1657
[44 empty] | 1658 | [87 empty] | 1658 | [86 empty] | 1658
[44 empty] | 1659 | [87 empty] | 1659 | [86 empty] | 1659
[44 empty] | 1660 | [87 empty] | 1660 | [86 empty] | 1660
[44 empty] | 1661 | [87 empty] | 1661 | [86 empty] | 1661
[44 empty] | 1662 | [87 empty] | 1662 | [86 empty] | 1662
[44 empty] | 1663 | [87 empty] | 1663 | [86 empty] | 1663
[44 empty] | 1664 | [87 empty] | 1664 | [86 empty] | 1664
[44 empty] | 1665 | [87 empty] | 1665 | [86 empty] | 1665
[44 empty] | 1666 | [87 empty] | 1666 | [86 empty] | 1666
[44 empty] | 1667 | [87 empty] | 1667 | [86 empty] | 1667
[44 empty] | 1668 | [87 empty] | 1668 | [86 empty] | 1668
[44 empty] | 1669 | [87 empty] | 1669 | [86 empty] | 1669
[44 empty] | 1670 | [87 empty] | 1670 | [86 empty] | 1670
[44 empty] | 1671 | [87 empty] | 1671 | [86 empty] | 1671
[44 empty] | 1672 | [87 empty] | 1672 | [86 empty] | 1672
[44 empty] | 1673 | [87 empty] | 1673 | [86 empty] | 1673
[44 empty] | 1674 | [87 empty] | 1674 | [86 empty] | 1674
[44 empty] | 1675 | [87 empty] | 1675 | [86 empty] | 1675
[44 empty] | 1676 | [87 empty] | 1676 | [86 empty] | 1676
[44 empty] | 1677 | [87 empty] | 1677 | [86 empty] | 1677
[44 empty] | 1678 | [87 empty] | 1678 | [86 empty] | 1678
[44 empty] | 1679 | [87 empty] | 1679 | [86 empty] | 1679
[44 empty] | 1680 | [87 empty] | 1680 | [86 empty] | 1680
[44 empty] | 1681 | [87 empty] | 1681 | [86 empty] | 1681
[44 empty] | 1682 | [87 empty] | 1682 | [86 empty] | 1682
[44 empty] | 1683 | [87 empty] | 1683 | [86 empty] | 1683
[44 empty] | 1684 | [87 empty] | 1684 | [86 empty] | 1684
[44 empty] | 1685 | [87 empty] | 1685 | [86 empty] | 1685
[44 empty] | 1686 | [87 empty] | 1686 | [86 empty] | 1686
[44 empty] | 1687 | [87 empty] | 1687 | [86 empty] | 1687
[44 empty] | 1688 | [87 empty] | 1688 | [86 empty] | 1688
[44 empty] | 1689 | [87 empty] | 1689 | [86 empty] | 1689
[44 empty] | 1690 | [87 empty] | 1690 | [86 empty] | 1690
[44 empty] | 1691 | [87 empty] | 1691 | [86 empty] | 1691
[44 empty] | 1692 | [87 empty] | 1692 | [86 empty] | 1692
[44 empty] | 1693 | [87 empty] | 1693 | [86 empty] | 1693
[44 empty] | 1694 | [87 empty] | 1694 | [86 empty] | 1694
[44 empty] | 1695 | [87 empty] | 1695 | [86 empty] | 1695
[44 empty] | 1696 | [87 empty] | 1696 | [86 empty] | 1696
[44 empty] | 1697 | [87 empty] | 1697 | [86 empty] | 1697
[44 empty] | 1698 | [87 empty] | 1698 | [86 empty] | 1698
[44 empty] | 1699 | [87 empty] | 1699 | [86 empty] | 1699
[44 empty] | 1700 | [87 empty] | 1700 | [86 empty] | 1700
[44 empty] | 1701 | [87 empty] | 1701 | [86 empty] | 1701
[44 empty] | 1702 | [87 empty] | 1702 | [86 empty] | 1702
[44 empty] | 1703 | [87 empty] | 1703 | [86 empty] | 1703
[44 empty] | 1704 | [87 empty] | 1704 | [86 empty] | 1704
[44 empty] | 1705 | [87 empty] | 1705 | [86 empty] | 1705
[44 empty] | 1706 | [87 empty] | 1706 | [86 empty] | 1706
[44 empty] | 1707 | [87 empty] | 1707 | [86 empty] | 1707
[44 empty] | 1708 | [87 empty] | 1708 | [86 empty] | 1708
[44 empty] | 1709 | [87 empty] | 1709 | [86 empty] | 1709
[44 empty] | 1710 | [87 empty] | 1710 | [86 empty] | 1710
[44 empty] | 1711 | [87 empty] | 1711 | [86 empty] | 1711
[44 empty] | 1712 | [87 empty] | 1712 | [86 empty] | 1712
[44 empty] | 1713 | [87 empty] | 1713 | [86 empty] | 1713
[44 empty] | 1714 | [87 empty] | 1714 | [86 empty] | 1714
[44 empty] | 1715 | [87 empty] | 1715 | [86 empty] | 1715
[44 empty] | 1716 | [87 empty] | 1716 | [86 empty] | 1716
[44 empty] | 1717 | [87 empty] | 1717 | [86 empty] | 1717
[44 empty] | 1718 | [87 empty] | 1718 | [86 empty] | 1718
[44 empty] | 1719 | [87 empty] | 1719 | [86 empty] | 1719
[44 empty] | 1720 | [87 empty] | 1720 | [86 empty] | 1720
[44 empty] | 1721 | [87 empty] | 1721 | [86 empty] | 1721
[44 empty] | 1722 | [87 empty] | 1722 | [86 empty] | 1722
[44 empty] | 1723 | [87 empty] | 1723 | [86 empty] | 1723
[44 empty] | 1724 | [87 empty] | 1724 | [86 empty] | 1724
[44 empty] | 1725 | [87 empty] | 1725 | [86 empty] | 1725
[44 empty] | 1726 | [87 empty] | 1726 | [86 empty] | 1726
[44 empty] | 1727 | [87 empty] | 1727 | [86 empty] | 1727
[44 empty] | 1728 | [87 empty] | 1728 | [86 empty] | 1728
[44 empty] | 1729 | [87 empty] | 1729 | [86 empty] | 1729
[44 empty] | 1730 | [87 empty] | 1730 | [86 empty] | 1730
[44 empty] | 1731 | [87 empty] | 1731 | [86 empty] | 1731
[44 empty] | 1732 | [87 empty] | 1732 | [86 empty] | 1732
[44 empty] | 1733 | [87 empty] | 1733 | [86 empty] | 1733
[44 empty] | 1734 | [87 empty] | 1734 | [86 empty] | 1734
[44 empty] | 1735 | [87 empty] | 1735 | [86 empty] | 1735
[44 empty] | 1736 | [87 empty] | 1736 | [86 empty] | 1736
[44 empty] | 1737 | [87 empty] | 1737 | [86 empty] | 1737
[44 empty] | 1738 | [87 empty] | 1738 | [86 empty] | 1738
[44 empty] | 1739 | [87 empty] | 1739 | [86 empty] | 1739
[44 empty] | 1740 | [87 empty] | 1740 | [86 empty] | 1740
[44 empty] | 1741 | [87 empty] | 1741 | [86 empty] | 1741
[44 empty] | 1742 | [87 empty] | 1742 | [86 empty] | 1742
[44 empty] | 1743 | [87 empty] | 1743 | [86 empty] | 1743
[44 empty] | 1744 | [87 empty] | 1744 | [86 empty] | 1744
[44 empty] | 1745 | [87 empty] | 1745 | [86 empty] | 1745
[44 empty] | 1746 | [87 empty] | 1746 | [86 empty] | 1746
[44 empty] | 1747 | [87 empty] | 1747 | [86 empty] | 1747
[44 empty] | 1748 | [87 empty] | 1748 | [86 empty] | 1748
[44 empty] | 1749 | [87 empty] | 1749 | [86 empty] | 1749
[44 empty] | 1750 | [87 empty] | 1750 | [86 empty] | 1750
[44 empty] | 1751 | [87 empty] | 1751 | [86 empty] | 1751
[44 empty] | 1752 | [87 empty] | 1752 | [86 empty] | 1752
[44 empty] | 1753 | [87 empty] | 1753 | [86 empty] | 1753
[44 empty] | 1754 | [87 empty] | 1754 | [86 empty] | 1754
[44 empty] | 1755 | [87 empty] | 1755 | [86 empty] | 1755
[44 empty] | 1756 | [87 empty] | 1756 | [86 empty] | 1756
[44 empty] | 1757 | [87 empty] | 1757 | [86 empty] | 1757
[44 empty] | 1758 | [87 empty] | 1758 | [86 empty] | 1758
[44 empty] | 1759 | [87 empty] | 1759 | [86 empty] | 1759
[44 empty] | 1760 | [87 empty] | 1760 | [86 empty] | 1760
[44 empty] | 1761 | [87 empty] | 1761 | [86 empty] | 1761
[44 empty] | 1762 | [87 empty] | 1762 | [86 empty] | 1762
[44 empty] | 1763 | [87 empty] | 1763 | [86 empty] | 1763
[44 empty] | 1764 | [87 empty] | 1764 | [86 empty] | 1764
[44 empty] | 1765 | [87 empty] | 1765 | [86 empty] | 1765
[44 empty] | 1766 | [87 empty] | 1766 | [86 empty] | 1766
[44 empty] | 1767 | [87 empty] | 1767 | [86 empty] | 1767
[44 empty] | 1768 | [87 empty] | 1768 | [86 empty] | 1768
[44 empty] | 1769 | [87 empty] | 1769 | [86 empty] | 1769
[44 empty] | 1770 | [87 empty] | 1770 | [86 empty] | 1770
[44 empty] | 1771 | [87 empty] | 1771 | [86 empty] | 1771
[44 empty] | 1772 | [87 empty] | 1772 | [86 empty] | 1772
[44 empty] | 1773 | [87 empty] | 1773 | [86 empty] | 1773
[44 empty] | 1774 | [87 empty] | 1774 | [86 empty] | 1774
[44 empty] | 1775 | [87 empty] | 1775 | [86 empty] | 1775
[44 empty] | 1776 | [87 empty] | 1776 | [86 empty] | 1776
[44 empty] | 1777 | [87 empty] | 1777 | [86 empty] | 1777
[44 empty] | 1778 | [87 empty] | 1778 | [86 empty] | 1778
[44 empty] | 1779 | [87 empty] | 1779 | [86 empty] | 1779
[44 empty] | 1780 | [87 empty] | 1780 | [86 empty] | 1780
[44 empty] | 1781 | [87 empty] | 1781 | [86 empty] | 1781
[44 empty] | 1782 | [87 empty] | 1782 | [86 empty] | 1782
[44 empty] | 1783 | [87 empty] | 1783 | [86 empty] | 1783
[44 empty] | 1784 | [87 empty] | 1784 | [86 empty] | 1784
[44 empty] | 1785 | [87 empty] | 1785 | [86 empty] | 1785
[44 empty] | 1786 | [87 empty] | 1786 | [86 empty] | 1786
[44 empty] | 1787 | [87 empty] | 1787 | [86 empty] | 1787
[44 empty] | 1788 | [87 empty] | 1788 | [86 empty] | 1788
[44 empty] | 1789 | [87 empty] | 1789 | [86 empty] | 1789
[44 empty] | 1790 | [87 empty] | 1790 | [86 empty] | 1790
[44 empty] | 1791 | [87 empty] | 1791 | [86 empty] | 1791
[44 empty] | 1792 | [87 empty] | 1792 | [86 empty] | 1792
[44 empty] | 1793 | [87 empty] | 1793 | [86 empty] | 1793
[44 empty] | 1794 | [87 empty] | 1794 | [86 empty] | 1794
[44 empty] | 1795 | [87 empty] | 1795 | [86 empty] | 1795
[44 empty] | 1796 | [87 empty] | 1796 | [86 empty] | 1796
[44 empty] | 1797 | [87 empty] | 1797 | [86 empty] | 1797
[44 empty] | 1798 | [87 empty] | 1798 | [86 empty] | 1798
[44 empty] | 1799 | [87 empty] | 1799 | [86 empty] | 1799
[44 empty] | 1800 | [87 empty] | 1800 | [86 empty] | 1800
[44 empty] | 1801 | [87 empty] | 1801 | [86 empty] | 1801
[44 empty] | 1802 | [87 empty] | 1802 | [86 empty] | 1802
[44 empty] | 1803 | [87 empty] | 1803 | [86 empty] | 1803
[44 empty] | 1804 | [87 empty] | 1804 | [86 empty] | 1804
[44 empty] | 1805 | [87 empty] | 1805 | [86 empty] | 1805
[44 empty] | 1806 | [87 empty] | 1806 | [86 empty] | 1806
[44 empty] | 1807 | [87 empty] | 1807 | [86 empty] | 1807
[44 empty] | 1808 | [87 empty] | 1808 | [86 empty] | 1808
[44 empty] | 1809 | [87 empty] | 1809 | [86 empty] | 1809
[44 empty] | 1810 | [87 empty] | 1810 | [86 empty] | 1810
[44 empty] | 1811 | [87 empty] | 1811 | [86 empty] | 1811
[44 empty] | 1812 | [87 empty] | 1812 | [86 empty] | 1812
[44 empty] | 1813 | [87 empty] | 1813 | [86 empty] | 1813
[44 empty] | 1814 | [87 empty] | 1814 | [86 empty] | 1814
[44 empty] | 1815 | [87 empty] | 1815 | [86 empty] | 1815
[44 empty] | 1816 | [87 empty] | 1816 | [86 empty] | 1816
[44 empty] | 1817 | [87 empty] | 1817 | [86 empty] | 1817
[44 empty] | 1818 | [87 empty] | 1818 | [86 empty] | 1818
[44 empty] | 1819 | [87 empty] | 1819 | [86 empty] | 1819
[44 empty] | 1820 | [87 empty] | 1820 | [86 empty] | 1820
[44 empty] | 1821 | [87 empty] | 1821 | [86 empty] | 1821
[44 empty] | 1822 | [87 empty] | 1822 | [86 empty] | 1822
[44 empty] | 1823 | [87 empty] | 1823 | [86 empty] | 1823
[44 empty] | 1824 | [87 empty] | 1824 | [86 empty] | 1824
[44 empty] | 1825 | [87 empty] | 1825 | [86 empty] | 1825
[44 empty] | 1826 | [87 empty] | 1826 | [86 empty] | 1826
[44 empty] | 1827 | [87 empty] | 1827 | [86 empty] | 1827
[44 empty] | 1828 | [87 empty] | 1828 | [86 empty] | 1828
[44 empty] | 1829 | [87 empty] | 1829 | [86 empty] | 1829
[44 empty] | 1830 | [87 empty] | 1830 | [86 empty] | 1830
[44 empty] | 1831 | [87 empty] | 1831 | [86 empty] | 1831
[44 empty] | 1832 | [87 empty] | 1832 | [86 empty] | 1832
[44 empty] | 1833 | [87 empty] | 1833 | [86 empty] | 1833
[44 empty] | 1834 | [87 empty] | 1834 | [86 empty] | 1834
[44 empty] | 1835 | [87 empty] | 1835 | [86 empty] | 1835
[44 empty] | 1836 | [87 empty] | 1836 | [86 empty] | 1836
[44 empty] | 1837 | [87 empty] | 1837 | [86 empty] | 1837
[44 empty] | 1838 | [87 empty] | 1838 | [86 empty] | 1838
[44 empty] | 1839 | [87 empty] | 1839 | [86 empty] | 1839
[44 empty] | 1840 | [87 empty] | 1840 | [86 empty] | 1840
[44 empty] | 1841 | [87 empty] | 1841 | [86 empty] | 1841
[44 empty] | 1842 | [87 empty] | 1842 | [86 empty] | 1842
[44 empty] | 1843 | [87 empty] | 1843 | [86 empty] | 1843
[44 empty] | 1844 | [87 empty] | 1844 | [86 empty] | 1844
[44 empty] | 1845 | [87 empty] | 1845 | [86 empty] | 1845
[44 empty] | 1846 | [87 empty] | 1846 | [86 empty] | 1846
[44 empty] | 1847 | [87 empty] | 1847 | [86 empty] | 1847
[44 empty] | 1848 | [87 empty] | 1848 | [86 empty] | 1848
[44 empty] | 1849 | [87 empty] | 1849 | [86 empty] | 1849
[44 empty] | 1850 | [87 empty] | 1850 | [86 empty] | 1850
[44 empty] | 1851 | [87 empty] | 1851 | [86 empty] | 1851
[44 empty] | 1852 | [87 empty] | 1852 | [86 empty] | 1852
[44 empty] | 1853 | [87 empty] | 1853 | [86 empty] | 1853
[44 empty] | 1854 | [87 empty] | 1854 | [86 empty] | 1854
[44 empty] | 1855 | [87 empty] | 1855 | [86 empty] | 1855
[44 empty] | 1856 | [87 empty] | 1856 | [86 empty] | 1856
[44 empty] | 1857 | [87 empty] | 1857 | [86 empty] | 1857
[44 empty] | 1858 | [87 empty] | 1858 | [86 empty] | 1858
[44 empty] | 1859 | [87 empty] | 1859 | [86 empty] | 1859
[44 empty] | 1860 | [87 empty] | 1860 | [86 empty] | 1860
[44 empty] | 1861 | [87 empty] | 1861 | [86 empty] | 1861
[44 empty] | 1862 | [87 empty] | 1862 | [86 empty] | 1862
[44 empty] | 1863 | [87 empty] | 1863 | [86 empty] | 1863
[44 empty] | 1864 | [87 empty] | 1864 | [86 empty] | 1864
[44 empty] | 1865 | [87 empty] | 1865 | [86 empty] | 1865
[44 empty] | 1866 | [87 empty] | 1866 | [86 empty] | 1866
[44 empty] | 1867 | [87 empty] | 1867 | [86 empty] | 1867
[44 empty] | 1868 | [87 empty] | 1868 | [86 empty] | 1868
[44 empty] | 1869 | [87 empty] | 1869 | [86 empty] | 1869
[44 empty] | 1870 | [87 empty] | 1870 | [86 empty] | 1870
[44 empty] | 1871 | [87 empty] | 1871 | [86 empty] | 1871
[44 empty] | 1872 | [87 empty] | 1872 | [86 empty] | 1872
[44 empty] | 1873 | [87 empty] | 1873 | [86 empty] | 1873
[44 empty] | 1874 | [87 empty] | 1874 | [86 empty] | 1874
[44 empty] | 1875 | [87 empty] | 1875 | [86 empty] | 1875
[44 empty] | 1876 | [87 empty] | 1876 | [86 empty] | 1876
Formulas:
Start = MIN([Start, row below]:AP135)
Start = MIN([Start, row below]:EA135)
Finish = MAX([Finish, row below]:AQ135)
Finish = MAX([Finish, row below]:EB135)
Actual = MIN([Actual, row below]:HK135)